## Prioritization Instructions
ITESC "Top 20" Prioritization Exercise
Desired Outcome:
► Identify the top technology projects for the university that best fit the qualifying characteristics based on the LUC strategic plan and goals
► Whittle down the list of projects "in-progress" to a manageable number and/or set appropriate expectations with regard to delivery dates
► Focus ITS resources on these projects
► Proactively manage resourcing issues in conjunction with the project capacity/availability of the organization
► Reset role expectations for project sponsors and project team members
Instructions:
► Reminder: 1) Project groupings for dependent or related projects ("Program Name" in column D) will receive one ranking.
However, projects within a single Program may have different priorities and delivery dates assigned and will be resourced accordingly.
2) Project sizing estimates using the "T-Shirt" method has been provided in column I for all projects.
X-Small = < 5 days, Small = 5-30 days, Medium = 31-60 days, Large = 61-120 Days, X-Large > 120 Days
3) Institutional Impact Statements are provided in column F on the Prioritization Worksheet.
► Each area represented on the IT Executive Steering Committee will submit one ranking sheet (1-20) of the top priority projects
For example, we'll receive one sheet from Finance, Human Resources, Development, Facilities, Academic Affairs, Student Affairs, and ITS.
► The "Prioritization Worksheet" tab within this spreadsheet will be used for this exercise. Using column G, "Your Ranking", rank your
projects from 1 to 20, where 1 is the most important. Do not rank the mandatory projects as work must be executed to support
standard institutional processes; they are sorted to the top of the list for your reference only.
► For your convenience, the projects already rated "high" by the Project Review Board are included in the Prioritization Worksheet tab,
as well as the new projects that have been submitted/requested since we developed the last Plan of Record.
We anticipate that the PRB has done a pretty good job of identifying the top projects and therefore, most of your top items will already be listed here.
Prior ITESC rankings are also shown in column H for your reference.
► The complete list of 151 projects is in the "FY09 Q3-Q4 Plan Of Record" tab, sorted by Priority (A=High, B=Medium, C=Low, M=Mandatory)
It is recommended that each committee member performs a cursory review of the B and C projects for prioritization consideration.
If you identify a B or C project that should be incorporated into your Top 20 ranking, please add it on one of the five blank lines at the
bottom of the Prioritization Worksheet. Column B ,"Row Nbr", will assist with moving between the 2 sheets.
► The list of the 67 completed is in the "FY09 Q1-Q2 Completed" tab, sorted by Priority.
Next Steps:
► Prioritized Worksheets are Due By: December 15th, 2008
► Submissions will be consolidated and reviewed at the January 8th, 2009 ITESC meeting
► Questions can be directed to Susan Malisch, 8-7750 or Jim Sibenaller, 8-7665

## Prioritization Worksheet
Pri | Row Nbr | PSS Nbr | Program Group | Project Desc | Institutional Impact Statement | Your Ranking | Prior Ranking | T-Shirt Sizing | Status | Est. Compl. (QTR) | Primary Customer
M | 137 |  | 4-Construction Projects | Construction Initiatives: - Burrowes House for Provost and President | Remodel the old Yellow house. | N/A | Not Previously Ranked | Medium | Active | Q3 | Facilities
M | 139 |  | 4-Construction Projects | WTC Data Center Remediation | Current data center lacks proper environmental services. This project will address required cooling and power needs. Temporary resolution approved and started. | N/A | Not Previously Ranked | Large | Active | Q4 | Information Technology Services
M | 141 |  | 4-Construction Projects | Construction Initiatives: - Coffey Hall remodeling | Entire building being remodeled | N/A | Not Previously Ranked | Large | Active | Q4+ | Facilities
M | 142 |  | 4-Construction Projects | Construction Initiatives: - 20-24 Chicago Ave. | New building on Chicago Avenue attached to 25 E | N/A | Not Previously Ranked | Large | Active | Q4+ | Facilities
M | 143 |  | 4-Construction Projects | Construction Initiatives: - Mundelein – Infrastructure Design & Implementation Multi - phased. | Mandated. In support of academic and facilities initiatives. | N/A | Not Previously Ranked | Large | Active | Q4+ | Facilities
M | 144 |  | 4-Construction Projects | Construction Initiatives: - 25 E law School Multi phased | Lewis Library and Law School Library are switching locations | N/A | Not Previously Ranked | Large | Active | Q4+ | Facilities
M | 145 |  | 4-Construction Projects | Construction Initiatives: - Crown Center Lower level | Upon relocation of servers remodel space for modern languages | N/A | Not Previously Ranked | Medium | Pending | Q4+ | Facilities
M | 146 |  | 4-Construction Projects | Construction Initiatives: - Sullivan Center | CAS to Sullivan | N/A | Not Previously Ranked | Small | Pending | Q4+ | Facilities
M | 147 |  | 4-Construction Projects | Construction Initiatives: - Granada Center | School of Nursing to Granada | N/A | Not Previously Ranked | Medium | Pending | Q4+ | Facilities
M | 148 |  | 4-Construction Projects | Construction Initiatives: - VSTC | Addition on to Gentile for Varsity sports | N/A | Not Previously Ranked | Medium | Pending | Q4+ | Facilities
M | 149 |  | 4-Construction Projects | Construction Initiatives: - Faculty / Staff lounge | New faculty staff lounge adjacent to Cudahy Science | N/A | Not Previously Ranked | Medium | Pending | Q4+ | Facilities
M | 150 |  | 4-Construction Projects | Construction Initiatives: - Damen Hall | Prepare for the razing of Damen Hall | N/A | Not Previously Ranked | Large | Pending | Q4+ | Facilities
M | 151 |  | 4-Construction Projects | Construction Initiatives: - Mundelein | Implement and academic server area adjacent to existing data room in lower level | N/A | Not Previously Ranked | Medium | Pending | Q4+ | Facilities
M | 136 |  | 4-Construction Projects | Construction Initiatives: - Lawson Lot (YMCA) | Mandated. In support of administration and facilities initiatives. | N/A | Not Previously Ranked | Small | Active | Q3 | Facilities
M | 138 |  | 4-Construction Projects | Construction Initiatives: - Remodel Terry Center | Mandated. In support of administration and facilities initiatives. | N/A | Not Previously Ranked | Medium | Active | Q3 | Facilities
M | 140 |  | 5-Security Projects | PCI/DSS Compliance | Compliance to the PCI/DSS standard is mandatory. Failure to comply with the standard can result in significant fines and a critical risk from a PR perspective. Additionally, if a breach of credit card data occurs while Loyola is non-compliant, Loyola would be forced to comply as a Level 1 merchant in addition to a multitude of additional fines. Total costs for such noncompliance or a breach could be significant. | N/A | Not Previously Ranked | X-Large | Active | Q4 | Finance
A | 1 | 196 | 3-LOCUS Enhancements | Enhancement to Locus - Federal Work Study project | Improve monitoring of FWS awards by automating Lawson payroll data to LOCUS. |  | 2 | Medium | Active | Q3 | Academic Affairs
A | 4 | 319 | 3-LOCUS Enhancements | LOCUS Enhancements: - Grade Change process | Automate grade change process for routine grade changes submitted by faculty. |  |  | Medium | Active | Q3 | Registration & Records
A | 5 | 641 | 3-LOCUS Enhancements | LOCUS Enhancements: - Load Previous Education to LOCUS from Grad R-Plus | Enhance preparation of commencement program & enhance student record completeness. |  |  | Large | Active | Q3 | Registration & Records
A | 9 | 799 | 3-LOCUS Enhancements | LOCUS Enhancements: - Update IPEDS Reporting related to race/ethnicity requirements. | Changes are needed to support the new IPEDS requirements. IPEDS now requires universities to report further detail on race and ethnicity. Data collection points such as applications will need to be altered as well as R+ appion and interface, SIS and associated reports. |  |  | Large | Active | Q4 | Registration & Records
A | 35 | 640 | 3-LOCUS Enhancements | LOCUS Enhancements: - Requested Rooms report over time by department and related reporting. | Provides the ability to review trends in academic space utilization. |  |  | Medium | Pending | Q1 | Registration & Records
A | 36 | 439 | 3-LOCUS Enhancements | LOCUS Enhancements: - Load AP/MDT test results to LOCUS | Automate currently manual processes of acquiring external placement/credit test results from authorized testing vendors. |  |  | Medium | Pending | Q2 | Enrollment Management
A | 7 | 869 | 3-LOCUS Enhancements | LOCUS Enhancements: - Add assessment grade capability for CORE classes. | Add assessment grade capability for CORE classes. |  |  | Medium | Active | Q3 | Office of the Provost
A | 13 | 805 | 3-LOCUS Enhancements | LOCUS Enhancements: - CS 9.0 Modifications (Planner & Messages) | CS 9.0 Modification - On SSS_MY_PLANNER page, the button "Plan by My Requirements" (SSS_PLAN_BY_REQ) should always be hidden. This is temporary, until we learn more about the Planner. Also, Message Catalog Entry - 14510,153 - Empty Planner message has been edited. Please include this entry in the project to be migrated. |  |  | X-Small | Active | Q3 | Registration & Records
A | 14 | 816 | 3-LOCUS Enhancements | LOCUS Enhancements: - Implement the PeopleSoft processing for SEVIS. | Implement the PeopleSoft processing for SEVIS. |  |  | Medium | Active | Q3 | International Affairs
A | 15 | 829 | 3-LOCUS Enhancements | LOCUS Enhancements: - Upgrade Peopletools to latest sub-release | Upgrade Peopletools to latest sub-release of PT 8.48 for the Campus Solutions environments |  |  | Medium | Active | Q3 | Information Technology Services
A | 16 | 844 | 3-LOCUS Enhancements | LOCUS Enhancements: - Modifications to delivered 1098T Reporting Process for calendar year 2007 reporting. | Modifications to delivered 1098T Reporting Process for calendar year 2007 reporting. If possible include the capability for students to access their 1098t online and print it themselves. This would not eliminate IT producing the 1098t for students as required by the government. We are waiting for the new, if any, requirements from the Federal government. |  |  | Small | Active | Q3 | Lawson Services
A | 17 | 858 | 3-LOCUS Enhancements | LOCUS Enhancements: - Archiving and purging student data | This project will examine options for archiving and purging student data to allow better performance times when processes run that manipulate large amounts of data. |  |  | Small | Active | Q3 | Office of The Bursar
A | 18 | 862 | 3-LOCUS Enhancements | LOCUS Enhancements: - State immunization registration requirements | Illinois state law requires that the University block students from registering for their second and subsequent semesters if they have not complied with the state immunization law requiring immunity from measles, mumps, rubella and tetanus/diphtheria. The current system blocks registration for lack of immunity to all the immunizations except tetanus/diphtheria. |  |  | Small | Active | Q3 | Wellness Center
A | 19 | 863 | 3-LOCUS Enhancements | LOCUS Enhancements: - Upgrade the TouchNet Component Interface to the lastest version, 5.0.3. | Upgrade the TouchNet Component Interface to the lastest version, 5.0.3. |  |  | Small | Active | Q3 | Information Technology Services
A | 21 | 873 | 3-LOCUS Enhancements | LOCUS Enhancements: Project SR320 (Apply For Graduation), certain Campus Community changes/customizations were requested. | In the development and testing of Project SR320 (Apply For Graduation), certain Campus Community changes/customizations were requested. These are: -Changing the 'Degree' name type to be called 'Diploma' -On the self-service Names page (SS_CC_NAME), additional text needs to be added to give students additional information about name changes. -On the grid, display a more complete Diploma name |  |  | Small | Active | Q3 | Registration & Records
A | 29 | 486 | 3-LOCUS Enhancements | At Room Capacity classes that have related classes. Problem occurs during auto entroll. | At Room Capacity classes that have related classes. Problem occurs during auto entroll. |  |  | Small | Pending | TBD | Registration & Records
A | 30 | 492 | 3-LOCUS Enhancements | Program/Plan screen: Requirement term of plan/subplan defaults to admit term. Review of the program/plan creation process is needed. | Program/Plan screen: Requirement term of plan/subplan defaults to admit term. Review of the program/plan creation process is needed |  |  | X-Small | Pending | TBD | Registration & Records
A | 31 | 494 | 3-LOCUS Enhancements | Modify the Academic Advisement Report. Currently it is too lengthy and visually unappealing. Advisors prefer to use their own handwritten advising worksheets. | Modify the Academic Advisement Report. Currently it is too lengthy and visually unappealing. Advisors prefer to use their own handwritten advising worksheets |  |  | Small | Pending | TBD | Registration & Records
A | 6 |  | 5-Security Projects | Personal Information Risk Group (PIRG) Disk Encryption Rollout | Identify and implement the necessary software, supporting procedures and training to identify and encrypt personally identifiable information (PII). Not implementing the software and corresponding procedures will result in an increased risk to the unwanted exposure of PII. |  | 3 | Large | Active | Q3 | Office of the President
A | 8 | 735 |  | This project will investigate, select, and implement an upgrade from our current Unix based Blackboard Transaction System to a system based on the windows operating system and a supported database. | From the SSR: "Upgrade the existing Campus Card transaction system to a windows-based system. This upgrade will provide a more user-friendly application and provide many potential savings... Enhance Campus Card functionality including: - improved process for issuing cards - point of sale transaction flow - interfaces with other systems such as RMS meal plans and MAXXESS security - improved reporting; and - easier maintenance. Note:Live date 5/1/2009 or later |  | 5 | Large | Active | Q4 | Finance
A | 10 | 830 |  | Enterprise Content Management (ECM)/Imaging Implementation | Provides a common method to store, share, process and manage documents in an effective and efficient manner, with ample opportunities to improve student services and build faster, more timely and secure single sources of information for faculty and administrative areas. Also a catalyst for process improvement. |  | 12 | X-Large | Active | Q4+ | Office of the Provost
A | 23 | 743 |  | Integrate the parking permit purchases from the web pages directly into the students account in PS, thereby eliminating the existing manual input of these changes. | Integrate the student parking permit purchases from the web pages directly into the students account in PS, thereby increasing efficiency by eliminating the existing manual input of these changes. Impacts Parking and Bursar's Office processes. |  | 16 | Medium | Pending | Q3 | FN-Parking/Business Services
A | 11 | 657 |  | Tuition Benefit Automation |  |  | 18 | Large | Active | Q4 | Human Resources
A | 2 | 800 |  | Business Intelligence/Data Warehouse Strategy Creation | Business Intelligence and Data Warehouse stragety definition needs to be completed in order to determine the future direction of our student reporting. The RDS needs to be replaced with a student data warehouse to help facilitate institutional reporting on current as well as historical reporting. Consideration needs to be given in the design for implementing a student centric warehouse with the ability to expand to an enterprise data warehouse as needed. |  | 21 | Large | Active | Q3 | Academic Affairs
A | 12 |  |  | Residential Wireless _ Campion Hall | Install wireless connectivty in Campion |  | Not Previously Ranked | Large | Active | Q1 | Student Affairs
A | 20 | 864 |  | This project is to bring the SSOM students financial aid processing and student billing into the LOCUS Oracle student system and retire the modules in the LUMC environment. Registration will be as a block type of registration ie individual classes will not be built in LOCUS. | This project is to bring the SSOM students financial aid processing and student billing into the LOCUS Oracle student system and retire the modules in the LUMC environment. Registration will be as a block type of registration ie individual classes will not be built in LOCUS. |  | Not Previously Ranked | Large | Active | Q3 | Finance-Office of VP-CFO
A | 3 | 868 | 2-Credit Card Processing | Credit Card Processing, Bursar |  |  | Not Previously Ranked | Medium | Active | Q3 | Finance
A | 22 | 624 | 6-“Housing / Scheduling” Projects | Rollout of the RMS Student Web Functionality | RMS Housing Application - Student Self Service |  | Not Previously Ranked | Large | Hold | Q4 | Student Affairs
A | 24 | 355 |  | Investigate and redesign as needed the Grad Merge process. Client would like to re-map PeopleSoft to BSR in order to ensure that we're capturing all of the information needed. | Investigate and redesign as needed the Grad Merge process. Client would like to re-map PeopleSoft to BSR in order to ensure that we're capturing all of the information needed. |  | Not Previously Ranked | Small | Pending | TBD | Development & Donor Services
A | 25 | 378 |  | Create a report/Excel spreadsheet to provide information about currently enrolled students that will be prohibited from registering because they do not meet immunization requirements. (Have a service indicator of 'WMM') May be able to modify the "Hold" report. Currently a PS query is being used. | Create a report/Excel spreadsheet to provide information about currently enrolled students that will be prohibited from registering because they do not meet immunization requirements. (Have a service indicator of 'WMM') May be able to modify the "Hold" report. Currently a PS query is being used. |  | Not Previously Ranked | X-Small | Pending | TBD | Wellness Center
A | 26 | 379 |  | Create a report of students who do not meet specific immunization requirements (measles, mumps, etc.) Selection criteria should include 'term' for which the student is 'term activated' | Create a report of students who do not meet specific immunization requirements (measles, mumps, etc.) Selection criteria should include 'term' for which the student is 'term activated' |  | Not Previously Ranked | X-Small | Pending | TBD | Wellness Center
A | 27 | 380 |  | Create a report of immunizations counts as required by the state. (Report exists in Web Focus, but needs to run via Dashboard with a selection criteria of term) | Create a report of immunizations counts as required by the state. (Report exists in Web Focus, but needs to run via Dashboard with a selection criteria of term) |  | Not Previously Ranked | X-Small | Pending | TBD | Wellness Center
A | 28 | 382 |  | Investigate and redesign as needed the Rome merge process. Client would like to re-map PeopleSoft to BSR in order to ensure that we're capturing all of the information needed. | Investigate and redesign as needed the Rome merge process. Client would like to re-map PeopleSoft to BSR in order to ensure that we're capturing all of the information needed. |  | Not Previously Ranked | X-Small | Pending | TBD | Development & Donor Services
A | 32 | 496 |  | Redesign BSR/Lawson GL interface, including reports utilized by both Gift Processing and Finance to reconcile gifts. | Redesign BSR/Lawson GL interface, including reports utilized by both Gift Processing and Finance to reconcile gifts. |  | Not Previously Ranked | Small | Pending | TBD | Development & Donor Services
A | 33 | 865 |  | Online client service training program | The purpose of the project is to enhance the quality of the client interaction (internal and external). This supports the universitys strategic plan of improving client service to enhance the Loyola experience for parents and students. We hope to ultimately positively impact enrollment and retention by developing and implementing an online client service training program geared toward higher-ed. |  | Not Previously Ranked | Medium | Pending | TBD | Provost's Office
A | 34 |  |  | Tuition Payment Plan | Design and develop a Tuition Payment Plan to replace the outsorced TMS application. |  | Not Previously Ranked | X-Large | Pending | TBD | Finance-Office of VP-CFO

## FY09 Q3-Q4 Plan Of Record
[6 empty] | Plan of Record Data - Key Fields | [5 empty] | Plan of Record Data - New Fields
151
Row Nbr | PSS Nbr | Level | Priority | Program Number | Program Group Name | Project Desc | Major Initiative/Ring Desc | Institutional Impact Statement | Strategic Category | Est. Compl. (QTR) | T-Shirt Sizing | Targeted Start Month (MM/YYYY) | Targeted Finish Month (MM/YYYY) | Status | Health | Primary Customer | Goal Alignment
1 | 196 | R | A | 3 | LOCUS Enhancements | Enhancement to Locus - Federal Work Study project | LOCUS Enhancements (19) | Improve monitoring of FWS awards by automating Lawson payroll data to LOCUS. | Academic & Faculty Support | Q3 | Medium | 2006-07-01 | 2009-01-01 | Active | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | Academic Affairs | 9: Promote a culture of service excellence at all levels.
2 | 800 | R | A |  |  | Business Intelligence/Data Warehouse Strategy Creation | Business Intelligence/Data Warehouse Strategy | Business Intelligence and Data Warehouse stragety definition needs to be completed in order to determine the future direction of our student reporting. The RDS needs to be replaced with a student data warehouse to help facilitate institutional reporting on current as well as historical reporting. Consideration needs to be given in the design for implementing a student centric warehouse with the ability to expand to an enterprise data warehouse as needed. | Administrative Initiatives | Q3 | Large | 2008-11-10 | 2009-01-01 | Active | Green - On Target, No Risk | Academic Affairs | 5: Improve the academic quality of incoming students and academic programs.
3 | 868 |  | A | 2 | Credit Card Processing | Credit Card Processing, Bursar | Credit Card Processing | Credit Card Processing, Bursar | Administrative Initiatives | Q3 | Medium | 2008-11-01 | 2009-02-01 | Active | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | Finance | 9: Promote a culture of service excellence at all levels.
4 | 319 | R | A | 3 | LOCUS Enhancements | LOCUS Enhancements: - Grade Change process | LOCUS Enhancements (19) | Automate grade change process for routine grade changes submitted by faculty. | Academic & Faculty Support | Q3 | Medium | 2007-05-07 | 2009-03-01 | Active | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | AA-Registration & Records | 9: Promote a culture of service excellence at all levels.
5 | 641 | R | A | 3 | LOCUS Enhancements | LOCUS Enhancements: - Load Previous Education to LOCUS from Grad R-Plus | LOCUS Enhancements (19) | Enhance preparation of commencement program & enhance student record completeness. | Academic & Faculty Support | Q3 | Large | 2007-06-01 | 2009-03-01 | Active | Yellow - Target in Jeopardy, Risks Being Managed, Unknowns Exist | AA-Registration & Records | 9: Promote a culture of service excellence at all levels.
6 |  | R | A | 5 | Security Projects | Personal Information Risk Group (PIRG) Disk Encryption Rollout | Security Initiatives (PIRG & Audit Related) | Identify and implement the necessary software, supporting procedures and training to identify and encrypt personally identifiable information (PII). Not implementing the software and corresponding procedures will result in an increased risk to the unwanted exposure of PII. | Continuous Service Development | Q3 | Large | 2007-11-01 | 2009-03-01 | Active | Yellow - Target in Jeopardy, Risks Being Managed, Unknowns Exist | Office of the President | 9: Promote a culture of service excellence at all levels.
7 | 869 |  | A | 3 | LOCUS Enhancements | LOCUS Enhancements: - Add assessment grade capability for CORE classes. | LOCUS Enhancements (19) | Add assessment grade capability for CORE classes. | Academic & Faculty Support | Q3 | Medium | 2008-11-01 | 2009-03-01 | Active | Green - On Target, No Risk | AA-Office of the Provost
8 | 735 | R | A |  |  | This project will investigate, select, and implement an upgrade from our current Unix based Blackboard Transaction System to a system based on the windows operating system and a supported database. | Campus Card System Replacement | From the SSR: "Upgrade the existing Campus Card transaction system to a windows-based system. This upgrade will provide a more user-friendly application and provide many potential savings... Enhance Campus Card functionality including: - improved process for issuing cards - point of sale transaction flow - interfaces with other systems such as RMS meal plans and MAXXESS security - improved reporting; and - easier maintenance. Note:Live date 5/1/2009 or later | Infrastructure | Q4 | Large | 2007-10-01 | 2009-05-01 | Active | Green - On Target, No Risk | Finance | 3: Enhance the quality of campus life for resident and commuter students.
9 | 799 | R | A | 3 | LOCUS Enhancements | LOCUS Enhancements: - Update IPEDS Reporting related to race/ethnicity requirements. | LOCUS Enhancements (19) | Changes are needed to support the new IPEDS requirements. IPEDS now requires universities to report further detail on race and ethnicity. Data collection points such as applications will need to be altered as well as R+ appion and interface, SIS and associated reports. | Student Technology Support | Q4 | Large | 2008-08-01 | 2009-06-01 | Active | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | AA-Registration & Records | 9: Promote a culture of service excellence at all levels.
10 | 830 | R | A |  |  | Enterprise Content Management (ECM)/Imaging Implementation | ECM/Imaging Implementation | Provides a common method to store, share, process and manage documents in an effective and efficient manner, with ample opportunities to improve student services and build faster, more timely and secure single sources of information for faculty and administrative areas. Also a catalyst for process improvement. | Administrative Initiatives | Q4+ | X-Large | 2008-07-01 | 2009-06-01 | Active | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | AA-Office of the Provost | 9: Promote a culture of service excellence at all levels.
11 | 657 | R | A |  |  | Tuition Benefit Automation | Tuition Benefit Automation | Tuition Benefit Automation | Student Technology Support | Q4 | Large | 2007-05-01 | 2009-06-01 | Active | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | Human Resources | 9: Promote a culture of service excellence at all levels.
12 |  | R | A |  |  | Residential Wireless _ Campion Hall | Wireless Expansion | Install wireless connectivty in Campion | Infrastructure | Q1 | Large | 2008-12-01 | 2009-08-01 | Active | Green - On Target, No Risk | Student Affairs
13 | 805 |  | A | 3 | LOCUS Enhancements | LOCUS Enhancements: - CS 9.0 Modifications (Planner & Messages) | LOCUS Enhancements (19) | CS 9.0 Modification - On SSS_MY_PLANNER page, the button "Plan by My Requirements" (SSS_PLAN_BY_REQ) should always be hidden. This is temporary, until we learn more about the Planner. Also, Message Catalog Entry - 14510,153 - Empty Planner message has been edited. Please include this entry in the project to be migrated. | Student Technology Support | Q3 | X-Small | N/A | 2009-01-01 | Active | Green - On Target, No Risk | Registration & Records
14 | 816 |  | A | 3 | LOCUS Enhancements | LOCUS Enhancements: - Implement the PeopleSoft processing for SEVIS. | LOCUS Enhancements (19) | Implement the PeopleSoft processing for SEVIS. | Administrative Initiatives | Q3 | Medium | N/A | 2009-01-01 | Active | Green - On Target, No Risk | International Affairs
15 | 829 |  | A | 3 | LOCUS Enhancements | LOCUS Enhancements: - Upgrade Peopletools to latest sub-release | LOCUS Enhancements (19) | Upgrade Peopletools to latest sub-release of PT 8.48 for the Campus Solutions environments | Administrative Initiatives | Q3 | Medium | N/A | 2009-03-01 | Active | Green - On Target, No Risk | Information Technology Services
16 | 844 |  | A | 3 | LOCUS Enhancements | LOCUS Enhancements: - Modifications to delivered 1098T Reporting Process for calendar year 2007 reporting. | LOCUS Enhancements (19) | Modifications to delivered 1098T Reporting Process for calendar year 2007 reporting. If possible include the capability for students to access their 1098t online and print it themselves. This would not eliminate IT producing the 1098t for students as required by the government. We are waiting for the new, if any, requirements from the Federal government. | Student Technology Support | Q3 | Small | N/A | 2009-01-01 | Active | Green - On Target, No Risk | Lawson Services
17 | 858 |  | A | 3 | LOCUS Enhancements | LOCUS Enhancements: - Archiving and purging student data | LOCUS Enhancements (19) | This project will examine options for archiving and purging student data to allow better performance times when processes run that manipulate large amounts of data. | Administrative Initiatives | Q3 | Small | N/A | 2009-01-01 | Active | Green - On Target, No Risk | Office of The Bursar
18 | 862 |  | A | 3 | LOCUS Enhancements | LOCUS Enhancements: - State immunization registration requirements | LOCUS Enhancements (19) | Illinois state law requires that the University block students from registering for their second and subsequent semesters if they have not complied with the state immunization law requiring immunity from measles, mumps, rubella and tetanus/diphtheria. The current system blocks registration for lack of immunity to all the immunizations except tetanus/diphtheria. | Academic & Faculty Support | Q3 | Small | N/A | 2009-01-01 | Active | Green - On Target, No Risk | Wellness Center
19 | 863 |  | A | 3 | LOCUS Enhancements | LOCUS Enhancements: - Upgrade the TouchNet Component Interface to the lastest version, 5.0.3. | LOCUS Enhancements (19) | Upgrade the TouchNet Component Interface to the lastest version, 5.0.3. | Administrative Initiatives | Q3 | Small | N/A | 2009-02-01 | Active | Green - On Target, No Risk | Information Technology Services
20 | 864 |  | A |  |  | This project is to bring the SSOM students financial aid processing and student billing into the LOCUS Oracle student system and retire the modules in the LUMC environment. Registration will be as a block type of registration ie individual classes will not be built in LOCUS. |  | This project is to bring the SSOM students financial aid processing and student billing into the LOCUS Oracle student system and retire the modules in the LUMC environment. Registration will be as a block type of registration ie individual classes will not be built in LOCUS. | Administrative Initiatives | Q3 | Large | N/A | 2009-03-01 | Active | Green - On Target, No Risk | Finance-Office of VP-CFO
21 | 873 |  | A | 3 | LOCUS Enhancements | LOCUS Enhancements: Project SR320 (Apply For Graduation), certain Campus Community changes/customizations were requested. | LOCUS Enhancements (19) | In the development and testing of Project SR320 (Apply For Graduation), certain Campus Community changes/customizations were requested. These are: -Changing the 'Degree' name type to be called 'Diploma' -On the self-service Names page (SS_CC_NAME), additional text needs to be added to give students additional information about name changes. -On the grid, display a more complete Diploma name | Student Technology Support | Q3 | Small | N/A | 2009-01-01 | Active | Green - On Target, No Risk | Registration & Records
22 | 624 | R | A | 6 | “Housing / Scheduling” Projects | Rollout of the RMS Student Web Functionality | RMS Housing Application Improvements | RMS Housing Application - Student Self Service | Student Technology Support | Q4 | Large | 2007-10-01 | 2009-06-01 | Hold | Yellow - Target in Jeopardy, Risks Being Managed, Unknowns Exist | Student Affairs | 3: Enhance the quality of campus life for resident and commuter students.
23 | 743 | R | A |  |  | Integrate the parking permit purchases from the web pages directly into the students account in PS, thereby eliminating the existing manual input of these changes. | Parking Permit Purchases Integration to PeopleSoft | Integrate the student parking permit purchases from the web pages directly into the students account in PS, thereby increasing efficiency by eliminating the existing manual input of these changes. Impacts Parking and Bursar's Office processes. | Administrative Initiatives | Q3 | Medium | 2009-01-01 | 2009-03-01 | Pending | Green - On Target, No Risk | FN-Parking/Business Services | 9: Promote a culture of service excellence at all levels.
24 | 355 |  | A |  |  | Investigate and redesign as needed the Grad Merge process. Client would like to re-map PeopleSoft to BSR in order to ensure that we're capturing all of the information needed. |  | Investigate and redesign as needed the Grad Merge process. Client would like to re-map PeopleSoft to BSR in order to ensure that we're capturing all of the information needed. | Administrative Initiatives | TBD | Small | TBD | TBD | Pending | Green - On Target, No Risk | Development & Donor Services
25 | 378 |  | A |  |  | Create a report/Excel spreadsheet to provide information about currently enrolled students that will be prohibited from registering because they do not meet immunization requirements. (Have a service indicator of 'WMM') May be able to modify the "Hold" report. Currently a PS query is being used. |  | Create a report/Excel spreadsheet to provide information about currently enrolled students that will be prohibited from registering because they do not meet immunization requirements. (Have a service indicator of 'WMM') May be able to modify the "Hold" report. Currently a PS query is being used. | Administrative Initiatives | TBD | X-Small | TBD | TBD | Pending | Green - On Target, No Risk | Wellness Center
26 | 379 |  | A |  |  | Create a report of students who do not meet specific immunization requirements (measles, mumps, etc.) Selection criteria should include 'term' for which the student is 'term activated' |  | Create a report of students who do not meet specific immunization requirements (measles, mumps, etc.) Selection criteria should include 'term' for which the student is 'term activated' | Administrative Initiatives | TBD | X-Small | TBD | TBD | Pending | Green - On Target, No Risk | Wellness Center
27 | 380 |  | A |  |  | Create a report of immunizations counts as required by the state. (Report exists in Web Focus, but needs to run via Dashboard with a selection criteria of term) |  | Create a report of immunizations counts as required by the state. (Report exists in Web Focus, but needs to run via Dashboard with a selection criteria of term) | Administrative Initiatives | TBD | X-Small | TBD | TBD | Pending | Green - On Target, No Risk | Wellness Center
28 | 382 |  | A |  |  | Investigate and redesign as needed the Rome merge process. Client would like to re-map PeopleSoft to BSR in order to ensure that we're capturing all of the information needed. |  | Investigate and redesign as needed the Rome merge process. Client would like to re-map PeopleSoft to BSR in order to ensure that we're capturing all of the information needed. | Administrative Initiatives | TBD | X-Small | TBD | TBD | Pending | Green - On Target, No Risk | Development & Donor Services
29 | 486 |  | A |  | LOCUS Enhancements | At Room Capacity classes that have related classes. Problem occurs during auto entroll. |  | At Room Capacity classes that have related classes. Problem occurs during auto entroll. | Administrative Initiatives | TBD | Small | TBD | TBD | Pending | Green - On Target, No Risk | Registration & Records
30 | 492 |  | A |  | LOCUS Enhancements | Program/Plan screen: Requirement term of plan/subplan defaults to admit term. Review of the program/plan creation process is needed |  | Program/Plan screen: Requirement term of plan/subplan defaults to admit term. Review of the program/plan creation process is needed | Administrative Initiatives | TBD | X-Small | TBD | TBD | Pending | Green - On Target, No Risk | Registration & Records
31 | 494 |  | A |  | LOCUS Enhancements | Modify the Academic Advisement Report. Currently it is too lengthy and visually unappealing. Advisors prefer to use their own handwritten advising worksheets |  | Modify the Academic Advisement Report. Currently it is too lengthy and visually unappealing. Advisors prefer to use their own handwritten advising worksheets | Administrative Initiatives | TBD | Small | TBD | TBD | Pending | Green - On Target, No Risk | Registration & Records
32 | 496 |  | A |  |  | Redesign BSR/Lawson GL interface, including reports utilized by both Gift Processing and Finance to reconcile gifts. |  | Redesign BSR/Lawson GL interface, including reports utilized by both Gift Processing and Finance to reconcile gifts. | Administrative Initiatives | TBD | Small | TBD | TBD | Pending | Green - On Target, No Risk | Development & Donor Services
33 | 865 |  | A |  |  | Online client service training program |  | The purpose of the project is to enhance the quality of the client interaction (internal and external). This supports the universitys strategic plan of improving client service to enhance the Loyola experience for parents and students. We hope to ultimately positively impact enrollment and retention by developing and implementing an online client service training program geared toward higher-ed | Continuous Service Development | TBD | Medium | TBD | TBD | Pending | Green - On Target, No Risk | Provost's Office
34 |  |  | A |  |  | Tuition Payment Plan to replace the outsorced TMS application. |  | Design and develop a Tuition Payment Plan to replace the outsorced TMS application | Administrative Initiatives | TBD | X-Large | TBD | TBD | Pending | Green - On Target, No Risk | Finance-Office of VP-CFO
35 | 640 |  | A | 3 | Room Utilization Reporting | LOCUS Enhancements: - Requested Rooms report over time by department and related reporting. | LOCUS Enhancements (19) | Provides the ability to review trends in academic space utilization. | Administrative Initiatives | Q1 | Medium | 2007-06-01 | TBD | Pending | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | AA-Registration & Records | 9: Promote a culture of service excellence at all levels.
36 | 439 | R | A | 3 | LOCUS Enhancements | LOCUS Enhancements: - Load AP/MDT test results to LOCUS | LOCUS Enhancements (19) | Automate currently manual processes of acquiring external placement/credit test results from authorized testing vendors. | Academic & Faculty Support | Q2 | Medium | 2007-10-01 | TBD | Pending | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | AA-Enrollment Management | 5: Improve the academic quality of incoming students and academic programs.
37 |  | R | B |  |  | Add technology “dashboard” metrics to ITS website for all of ITS | Develop ITS Services Direction & Metrics |  | Continuous Service Development | Q3 | Medium | 2008-06-01 | 2009-01-01 | Active | Green - On Target, No Risk | Academic Affairs | 9: Promote a culture of service excellence at all levels.
38 |  |  | B |  |  | Deploy Teamspot Application at Water Tower Campus |  | Teamspot Deployment | Continuous Service Development | Q3 | Small | 2008-04-01 | 2009-01-01 | Active | Green - On Target, No Risk | Academic Affairs
39 |  | R | B |  |  | Implement Crestron RoomView - Remote Management Software | Remote Electronic Classroom Management |  | Academic & Faculty Support | Q3 | Small | 2008-06-01 | 2009-01-01 | Active | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
40 |  |  | B |  |  | Develop, deploy and evaluate pilot for making online assessment through Blackboard more secure for high stakes testing, e.g., Respondus |  | Develop and deploy pilot for making online assessment through Blackboard more secure | Academic & Faculty Support | Q3 | Medium | 2008-09-01 | 2009-01-01 | Active | Green - On Target, No Risk | Academic Affairs
41 | 871 |  | B |  | LOCUS Enhancements | Review and update of enrollment error messages. |  |  | Student Technology Support | Q3 | Small | 2008-11-01 | 2009-01-01 | Active | Green - On Target, No Risk | AA-Registration & Records
42 |  |  | B | 5 | Security Projects | Security Audit - Response to Open Items - FY08 | Security Initiatives (PIRG & Audit Related) | Remediation of the high and medium risk items identified in the annual ITS security audit is required. Not implementing the recommendations will result in an increased risk to the overall information security of the institution. | Infrastructure | Q3 | Medium | 2007-08-01 | 2009-02-01 | Active | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | Office of the President
43 |  |  | B |  |  | Heat Knowledge Base |  | Knowledge Base activation | Continuous Service Development | Q3 | Medium | 2008-06-01 | 2009-02-01 | Active | Green - On Target, No Risk | Academic Affairs | 9: Promote a culture of service excellence at all levels.
44 |  |  | B |  |  | Define requirements and determine feasibility for setting up learning object repository |  | Develop requirements w/ Academic Affairs | Academic & Faculty Support | Q3 | Medium | 2008-06-01 | 2009-03-01 | Active | Green - On Target, No Risk | Academic Affairs | 1: Enrich its rigorous academic programs to better integrate the unique strengths and characteristics of a Jesuit and Catholic education.
45 |  |  | B |  |  | Develop and Propose ITS Certification Model |  | Develop and Propose ITS Certification Model | Administrative Initiatives | Q3 | Medium | 2008-06-01 | 2009-03-01 | Active | Green - On Target, No Risk | Academic Affairs | 1: Enrich its rigorous academic programs to better integrate the unique strengths and characteristics of a Jesuit and Catholic education.
46 | 850 |  | B |  | Webfocus upgrade | upgrade to 7.6.6 of toolset |  |  | Academic & Faculty Support | Q3 | Small | 2008-11-01 | 2009-03-01 | Active | Green - On Target, No Risk | AA-Registration & Records
47 |  |  | B |  |  | Network Initiative - Cell Phone coverage | Network Enhacement | Enhance Cell phone coverage for buildings along the lake front | Infrastructure | Q3 | Medium | 2008-10-01 | 2009-03-01 | Active | Green - On Target, No Risk | Information Technology Services
48 |  |  | B |  |  | Working with Academic Affairs, develop and implement support paradigm for Web 2.0 tools in teaching and learning, e.g., podcasting in Blackboard (covers training) |  | Working with Academic Affairs, develop and implement support paradigm for Web 2.0 tools in teaching and learning, e.g., podcasting in Blackboard (covers training) | Academic & Faculty Support | Q4 | Medium | 2008-05-01 | 2009-04-01 | Active | Green - On Target, No Risk | Academic Affairs
49 |  |  | B |  |  | Develop and Implement Summer Training Camps for Area High School Students |  | Offer Summer Training Camps and Clinics for Area Advanced High School Students | Academic & Faculty Support | Q4+ | Medium | 2008-06-01 | 2009-04-01 | Active | Green - On Target, No Risk | Academic Affairs | 8: Strengthen it relationship with the City of Chicago and the neighborhoods of the Water Tower, Lake Shore and Medical Center Campuses.
50 |  |  | B |  |  | Deliver Blackboard and other Technology Workshops w/Academic Affairs |  | Deliver Blackboard and other Technology Workshops w/Academic Affairs | Academic & Faculty Support | Q4 | Medium | 2008-05-01 | 2009-05-01 | Active | Green - On Target, No Risk | Academic Affairs
51 |  |  | B |  |  | Enhanced training initiatives and documentation to expand modes of delivery, e.g., narrated tutorials and use of Web 2.0 tools, e.g., blogs and wikis |  | Enhanced training initiatives and documentation to expand modes of delivery, e.g., narrated tutorials and use of Web 2.0 tools, e.g., blogs and wikis | Academic & Faculty Support | Q4 | Large | 2008-01-01 | 2009-05-01 | Active | Green - On Target, No Risk | Academic Affairs
52 |  |  | B |  |  | Working with Academic Affairs and Web Development, design and implement web "portal" to teaching and learning technologies |  | Working with Academic Affairs and Web Development, design and implement web "portal" to teaching and learning technologies | Academic & Faculty Support | Q4+ | Large | 2008-06-01 | 2009-05-01 | Active | Green - On Target, No Risk | Academic Affairs
53 |  | R | B |  |  | Develop long-term strategy for LMS |  | LMS Strategic Planning - (Blackboard Sourcing) | Academic & Faculty Support | Q4+ | X-Large | 2007-07-01 | 2009-05-01 | Active | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | Academic Affairs | 5: Improve the academic quality of incoming students and academic programs.
54 |  |  | B |  |  | Position support for Blackboard, Opinio, Research Support Systems, and Listserv Managemet for Self-Service Call Center |  | Position support for Blackboard, Opinio, Research Support Systems, and Listserv Managemet for Self-Service Call Center | Continuous Service Development | Q4 | Medium | 2008-06-01 | 2009-05-01 | Active | Green - On Target, No Risk | Academic Affairs
55 | 855 |  | B |  | Data Encryption | Secure database files | Business Continutity Disater Recovery | Encrypt the underlining database files on the servers | Infrastructure | Q4 | Large | 2008-10-01 | 2009-05-01 | Active | Green - On Target, No Risk | AA-Registration & Records
56 |  |  | B | 5 | Security Projects | Information Security Monitoring Program (IPS, vulenrability, app/pen testing) | Security Initiatives (PIRG & Audit Related) |  | Continuous Service Development | Q4 | Medium | 2008-11-01 | 2009-06-01 | Active | Green - On Target, No Risk | Information Technology Services
57 |  |  | B | 5 | Security Projects | Information Security Awareness | Security Initiatives (PIRG & Audit Related) |  | Continuous Service Development | Q4 | Small | 2008-08-01 | 2009-06-01 | Active | Green - On Target, No Risk | Information Technology Services
58 |  |  | B |  |  | Implementation of Storage Expansion - Faculty / Staff | Faculty/Staff Storage Expansion |  | Academic & Faculty Support | Q4 | Large | 2008-06-08 | 2009-06-01 | Active | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | Academic Affairs | 1: Enrich its rigorous academic programs to better integrate the unique strengths and characteristics of a Jesuit and Catholic education.
59 |  |  | B |  |  | Zen Configuration Management. This will require a rebuild of every application we currently use. | Zen Configuration Management | Improve Application deployment and asset management. | Continuous Service Development | Q4 | Large | 2008-06-08 | 2009-06-01 | Active | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
60 |  | R | B |  |  | Patching Policies and Metrics for OS Patch Management | Develop ITS Services Direction & Metrics | Improve on what is today a manual process. | Continuous Service Development | Q4 | Medium | 2007-11-01 | 2009-06-01 | Active | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
61 |  |  | B |  |  | Connectivity to the Wellness Center |  | Provide more reliable service for wellness Center application. Requires City ROW | Infrastructure | Q1 | Large | 2008-07-01 | 2009-07-01 | Active | Green - On Target, No Risk | Student Affairs | 3: Enhance the quality of campus life for resident and commuter students.
62 |  |  | B |  |  | Network Initiative - LSC | Network Enhacement | Roll out VOIP | Infrastructure | Q4+ | Small | 2008-05-01 | 2009-07-01 | Active | Green - On Target, No Risk | Information Technology Services
63 |  | R | B |  |  | Academic Wireless - Lewis Towers | Wireless Expansion | Expansion of wireless. Strengthens Loyola's competitiveness | Student Technology Support | Q1 | Large | 2009-01-01 | 2009-09-08 | Active | Green - On Target, No Risk | Academic Affairs | 1: Enrich its rigorous academic programs to better integrate the unique strengths and characteristics of a Jesuit and Catholic education.
64 |  |  | B |  |  | Cost Containment & Reduction - Implement local and long distance contracts - Combine DS1 Services into a coterminous agreement - Evaluate Desktop Support contract | Cost Containment & Reduction | Overall cost savings to the University | Administrative Initiatives | Q4+ | Small | 2007-07-01 | On-going | Active | Yellow - Target in Jeopardy, Risks Being Managed, Unknowns Exist | Information Technology Services | 9: Promote a culture of service excellence at all levels.
65 | 138 |  | B | 3 | LOCUS Enhancements | LOCUS Enhancements: - Establish process to update Campus Addresses automatically. All non-current residents need to have the CAMP address type inactivated. | LOCUS Enhancements (19) | Establish process to update Campus Addresses automatically. All non-current residents need to have the CAMP address type inactivated. | Administrative Initiatives | N/A | Small | N/A | N/A | Active | Green - On Target, No Risk | Information Technology Services
66 | 340 |  | B |  |  | Add faculty/staff to BSR for Capital Campaign solicitations. |  | Add faculty/staff to BSR for Capital Campaign solicitations. | Administrative Initiatives | N/A | Medium | N/A | N/A | Active | Green - On Target, No Risk | Development & Donor Services
67 | 836 |  | B | 3 | LOCUS Enhancements | LOCUS Enhancements: - An enhancement is needed that will re-activate(from Lawson) inactive accounts with the new effective dated row. | LOCUS Enhancements (19) | Account Units and Account Funds are updated in People Soft from Lawson with an Active or Inactive status. On occasion Lawson will re-activate an inactive account. This activity was not included in the current process. An enhancement is needed that will re-activate inactive accounts with the new effective dated row. | Administrative Initiatives | N/A | Small | N/A | N/A | Active | Green - On Target, No Risk | Lawson Services
68 | 837 |  | B |  |  | IRB would like to restructure the way it handles its records into a more efficient process than they currently have. Their current structure invovles functions in and between Access, Word, and Adobe. |  | IRB would like to restructure the way it handles its records into a more efficient process than they currently have. Their current structure invovles functions in and between Access, Word, and Adobe. | Administrative Initiatives | N/A | Medium | N/A | N/A | Active | Green - On Target, No Risk | Institutional Review Board
69 | 856 |  | B |  |  | Migrate current Oracle 9i/RMS 5.3.001.12 to Oracle 10g/RMS 5.3.005 as recommended by the vendor for all non-LOCUS and ADVANCE databases. Both LOCUS and Advance databases were upgraded to 10g with the upgrade of the application. |  | Migrate current Oracle 9i/RMS 5.3.001.12 to Oracle 10g/RMS 5.3.005 as recommended by the vendor for all non-LOCUS and ADVANCE databases. Both LOCUS and Advance databases were upgraded to 10g with the upgrade of the application. | Continuous Service Development | N/A | Small | N/A | N/A | Active | Green - On Target, No Risk | Information Technology Services
70 | 121 |  | B |  | LOCUS Enhancements | Design audit trail functionality for the use of the Enrollment page, which bypasses enrollment engine business rules. Page is used by Registration & Records staff when urgent enrollment updates are necessary or when updates for billing purposes are necessary. |  | Design audit trail functionality for the use of the Enrollment page, which bypasses enrollment engine business rules. Page is used by Registration & Records staff when urgent enrollment updates are necessary or when updates for billing purposes are necessary. | Administrative Initiatives | TBD | Medium | TBD | TBD | Hold | Green - On Target, No Risk | Registration & Records
71 | 128 |  | B |  |  | Bio-demo and pertinent information needs to be loaded automatically into RMS. |  | Bio-demo and pertinent information needs to be loaded automatically into RMS. | Administrative Initiatives | TBD | Large | TBD | TBD | Hold | Green - On Target, No Risk | Information Technology Services
72 | 186 |  | B |  |  | Create a process to export photo images of Loyola ID cards to the MaXxess security system |  | Create a process to export photo images of Loyola ID cards to the MaXxess security system | Administrative Initiatives | TBD | X-Small | TBD | TBD | Hold | Green - On Target, No Risk | Information Technology Services
73 | 462 |  | B |  |  | Create a WebFOCUS dashboard for the security officers to be able to pull up comprehensive data on a person. Possible substitute for MAXxess workstation in many cases (especially if update capability is not needed). |  | Create a WebFOCUS dashboard for the security officers to be able to pull up comprehensive data on a person. Possible substitute for MAXxess workstation in many cases (especially if update capability is not needed). | Continuous Service Development | TBD | Small | TBD | TBD | Hold | Green - On Target, No Risk | Campus Safety LSC
74 | 531 |  | B |  |  | Enable ldap authentication on static web pages (hector) using php. This would require ssl certificates on all the web servers, which we don't currently have. |  | Enable ldap authentication on static web pages (hector) using php. This would require ssl certificates on all the web servers, which we don't currently have. | Continuous Service Development | TBD | Small | TBD | TBD | Hold | Green - On Target, No Risk | Information Services
75 | 654 |  | B |  |  | BI-DW Business Intelligence - Data Warehousing Data Administration. |  | BI-DW Business Intelligence - Data Warehousing Data Administration. | Continuous Service Development | TBD | X-Small | TBD | TBD | Hold | Green - On Target, No Risk | Information Technology Services
76 | 700 |  | B |  |  | Enhancements to the Rambler Bucks charge authorization system. Currently, requests are collected on the web form and then entered manually in PeopleSoft and Blackboard. The new functionality requested would provided automated processes. Primary request is to post amount of Rambler Bucks requested by student to their account in PeopleSoft. Secondary request is to load Rambler Bucks amount into the Blackboard Transaction system. Requested delivery date - December 15, 2007 |  | Reduce the need for manual intervention in posting amounts to the students account in PeopleSoft and Blackboard | Administrative Initiatives | Q3 | Small | 2009-01-01 | 2009-02-01 | Pending | Green - On Target, No Risk | Finance | 9: Promote a culture of service excellence at all levels.
77 |  |  | B | 5 | Security Projects | Annual Information Security Assessment - FY09 | Security Initiatives (PIRG & Audit Related) |  | Continuous Service Development | Q4 | Medium | 2009-03-01 | 2009-05-01 | Pending | Green - On Target, No Risk | Information Technology Services
78 |  |  | B |  |  | Offer Digital Media Courses for Students, Faculty and Staff on a Variety of Topics, including: Video Production, Animation, Newspaper Construction, Website Design, Web 2.0, Scripting, etc. | Offer Digital Media Clinics & Seminars |  | Academic & Faculty Support | Q4+ | Medium | 2008-08-01 | On-going | Pending | Green - On Target, No Risk | AA-Colleges & Schools | 7: Expand its investment in research and scholarship in order to take full advantage of its academic strengths.
79 | 403 |  | B |  |  | The CAS budget office needs a report extracted from FAS-PT that would allow them to do their budget projections effectively each term. |  | The CAS budget office needs a report extracted from FAS-PT that would allow them to do their budget projections effectively each term. | Academic & Faculty Support | TBD | Small | TBD | TBD | Pending | Green - On Target, No Risk | Provost's Office
80 | 475 |  | B |  | LOCUS Enhancements | Add Reason code to identify change of registration per dean's permission to drop on enrollment request. Review nuances of Program Action Reason Code on the Program/Plan page. |  | Add Reason code to identify change of registration per dean's permission to drop on enrollment request. Review nuances of Program Action Reason Code on the Program/Plan page. | Academic & Faculty Support | TBD | Small | TBD | TBD | Pending | Green - On Target, No Risk | Registration & Records
81 | 478 |  | B |  | LOCUS Enhancements | Modification to registration for variable credit hours |  | Modification to registration for variable credit hours | Academic & Faculty Support | TBD | Small | TBD | TBD | Pending | Green - On Target, No Risk | Registration & Records
82 | 481 |  | B |  | LOCUS Enhancements | Thesis and Dissertation Committees have titles working great and a place for the director, but committees are kept in a separate database. Can we use the advisorts screens to keep records of whole committees and changes? |  | Thesis and Dissertation Committees have titles working great and a place for the director, but committees are kept in a separate database. Can we use the advisorts screens to keep records of whole committees and changes? | Academic & Faculty Support | TBD | X-Small | TBD | TBD | Pending | Green - On Target, No Risk | Registration & Records
83 | 485 |  | B |  | LOCUS Enhancements | Review transfer credit to determine whether prerequisites are satisfied and whether appointment times are correctly assigned |  | Review transfer credit to determine whether prerequisites are satisfied and whether appointment times are correctly assigned | Administrative Initiatives | TBD | X-Small | TBD | TBD | Pending | Green - On Target, No Risk | Registration & Records
84 | 544 |  | B |  | LOCUS Enhancements | Requesting a batch process to assign/unassign Undergraduate advisors to students based on pre-defined rules. |  | Requesting a batch process to assign/unassign Undergraduate advisors to students based on pre-defined rules. | Student Technology Support | TBD | Medium | TBD | TBD | Pending | Green - On Target, No Risk | Academic Advising and Services
85 | 545 |  | B |  | LOCUS Enhancements | Requesting changes to Self-service View My Advisers in LOCUS as accessed by students. Adviser role should be displayed to differentiate different academic advisors, faculty advisors, and school advisors. |  | Requesting changes to Self-service View My Advisers in LOCUS as accessed by students. Adviser role should be displayed to differentiate different academic advisors, faculty advisors, and school advisors. | Student Technology Support | TBD | Small | TBD | TBD | Pending | Green - On Target, No Risk | Academic Advising and Services
86 | 609 |  | B |  | LOCUS Enhancements | Modification to program that will create 1098Ts for Visiting Students who are placed in non-degree seeking programs BUT pay qualified expenses (tuition and fees)to Loyola, for calendar year 2007. Initially, would include Rome Center and Beijing Center Visiting students. Must wait until the CY 2007 version of the program is delivered by PS (may be late November) to finalize. |  | Modification to program that will create 1098Ts for Visiting Students who are placed in non-degree seeking programs BUT pay qualified expenses (tuition and fees)to Loyola, for calendar year 2007. Initially, would include Rome Center and Beijing Center Visiting students. Must wait until the CY 2007 version of the program is delivered by PS (may be late November) to finalize. | Student Technology Support | TBD | Small | TBD | TBD | Pending | Green - On Target, No Risk | Finance-Office Of Vp-Cfo
87 | 258 |  | C |  |  | Enhancements to Project Status System | Enhancements to Project Status System |  | Administrative Initiatives | Q3 | Large | 2007-01-01 | 2009-01-01 | Active | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
88 | 756 | R | C | 7 | BCDR/Failover | Install DataGuard on Advancement databases | Business Continuity Disaster Recovery | Provide a failover system to prevent database outage when production database fail | Infrastructure | Q3 | Small | 2007-10-01 | 2009-03-01 | Active | Green - On Target, No Risk | Advancement | 9: Promote a culture of service excellence at all levels.
89 | 757 | R | C | 7 | BCDR/Failover | Install DataGuard on LUC Databases (in house developed, R25, CMS, Opinio, etc.) | Business Continuity Disaster Recovery | Provide a failover system to prevent database outage when production database fail | Infrastructure | Q3 | Small | 2007-10-01 | 2009-03-01 | Active | Green - On Target, No Risk | AA-Office of the Provost | 9: Promote a culture of service excellence at all levels.
90 |  |  | C |  |  | Develop (with Academic Affairs) New Design for Learning Spaces | Develop (with Academic Affairs) New Design for Learning Spaces |  | Academic & Faculty Support | Q3 | X-Large | 2007-09-01 | 2009-03-01 | Active | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | Academic Affairs | 1: Enrich its rigorous academic programs to better integrate the unique strengths and characteristics of a Jesuit and Catholic education.
91 |  | R | C |  |  | Develop and deliver remote technology assistance in use of Blackboard and other teaching technologies for JFRC | Remote Electronic Classroom Management |  | Academic & Faculty Support | Q4 | Small | 2008-06-01 | 2009-05-01 | Active | Green - On Target, No Risk | Academic Affairs
92 |  |  | C |  |  | Rome Center Support (desktop, network, services, Skype) | Rome Center Technology Review | To assist in creating processes that will improve the delivery of services to students attending classes at JFRC. Also to begin laying the foundation for infrastructure requirements to support the new campus. | Continuous Service Development | Q4 | Medium | 2007-06-01 | 2009-06-01 | Active | Green - On Target, No Risk | Academic Affairs | 4: Strengthen the international dimensions of its programs and outreach.
93 |  |  | C |  |  | Phased Implementations: - Enterprise Architecture Principles & Framework | Next Phases on PMO, QA, Architecture |  | Continuous Service Development | Q4 | Medium | 2007-03-01 | 2009-06-01 | Active | Orange - Slightly Off Target, Several Risks or Unknowns | Information Technology Services | 9: Promote a culture of service excellence at all levels.
94 |  |  | C |  |  | Recommendation for Storage Expansion - Students | Recommendation for Storage Expansion - Students |  | Student Technology Support | Q4 | Small | 2008-11-01 | 2009-06-01 | Active | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | Information Technology Services | 9: Promote a culture of service excellence at all levels.
95 |  |  | C |  |  | Virtualization Initiative | Develop ITS Services Direction & Metrics | Develop and implement a virtualization strategy that will increase performance, availability and flexibilty while decreasing overall cost | Infrastructure | Q1 | Large | 2008-11-01 | 2009-07-01 | Active | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
96 |  |  | C |  |  | Evaluate the BB Community System |  | This is a portal that adds functionality to the BB LMS system. Allows for creation of groups and administration of those groups by non administrators. | Academic & Faculty Support | N/A | Small | N/A | N/A | Active | Green - On Target, No Risk
97 | 250 |  | C |  |  | Create a local source for RSS news items for selection on the portal. These news items should be updated at least nightly. |  | Create a local source for RSS news items for selection on the portal. These news items should be updated at least nightly. | Student Technology Support | N/A | Small | N/A | N/A | Active | Green - On Target, No Risk | Information Technology Services
98 | 446 |  | C |  |  | Office of University Advising Reports |  | Office of University Advising Reports | Academic & Faculty Support | N/A | Small | N/A | N/A | Active | Green - On Target, No Risk | Academic Advising and Services
99 | 693 |  | C | 3 | LOCUS Enhancements | LOCUS Enhancements: - Add translate value in Facility_partition in LOCUS (Info Commons) | LOCUS Enhancements (19) | Add translate value in Facility_partition in LOCUS. Information Commons partition is used in conjunction with new IC classrooms and LOCUS/R25 interface. Classrooms will be open in January, 2008. System update needed for classroom scheduling prep by October 1. | Administrative Initiatives | N/A | Small | N/A | N/A | Active | Green - On Target, No Risk | AA-Registration & Records
100 | 784 |  | C |  |  | WebTMA Implementation: We plan to upgrade the current work order system to a web-based version which will be easier to use for both the requestor and the user. It will be compatible with wireless handheld devices which allow the users to access work orders in the field. The upgraded system will have a greater capability for reporting features and information that can be retrieved from the wor |  | WebTMA Implementation: We plan to upgrade the current work order system to a web-based version which will be easier to use for both the requestor and the user. It will be compatible with wireless handheld devices which allow the users to access work orders in the field. The upgraded system will have a greater capability for reporting features and information that can be retrieved from the wor | Continuous Service Development | N/A | Small | N/A | N/A | Active | Green - On Target, No Risk | Facilities LSC
101 | 785 |  | C |  |  | Workgroup established to review issues involving I-9's, Visas, and other international forms. |  | Workgroup established to review issues involving I-9's, Visas, and other international forms. | Continuous Service Development | N/A | Large | N/A | N/A | Active | Green - On Target, No Risk | Human Resources
102 | 835 |  | C |  |  | ITS Web Site Redesign - The ITS website has been established with its current struture and most of its content for over 14 months now. Version 2 of the ITS website utilized the new content management system (CMS) and templates. As part of the first version we reviewed all content, removed hundreds of web pages, and reorganized the delivery of content. |  | ITS Web Site Redesign - The ITS website has been established with its current struture and most of its content for over 14 months now. Version 2 of the ITS website utilized the new content management system (CMS) and templates. As part of the first version we reviewed all content, removed hundreds of web pages, and reorganized the delivery of content. | Administrative Initiatives | N/A | Large | N/A | N/A | Active | Green - On Target, No Risk | Information Technology Services
103 | 838 |  | C | 3 | LOCUS Enhancements | LOCUS Enhancements: - Develop LU-specific queries to extend the usefulness of Population Select tool. | LOCUS Enhancements (19) | Develop LU-specific queries to extend the usefulness of Population Select tool. This development work will make the delivered tool more accessible for the end-user. One area that may be useful is Mass Assign/Mass Release of Service Indicators. Specific applications may include Extended Drop Exceptions for UGRD and Block-Enrolled Students for LAW. | Academic & Faculty Support | N/A | Small | N/A | N/A | Active | Green - On Target, No Risk | Registration & Records
104 | 859 |  | C |  |  | The office of Student Activities & Greek Affairs (SAGA) is interested in purchasing existing software that helps to streamline and manage student organization data. Our goals are: Simplify the org management system for both students and administrators Enhance the communication with student orgs Student org event registration Make sure students have completed all steps in order to hold an even |  | The office of Student Activities & Greek Affairs (SAGA) is interested in purchasing existing software that helps to streamline and manage student organization data. Our goals are: Simplify the org management system for both students and administrators Enhance the communication with student orgs Student org event registration Make sure students have completed all steps in order to hold an even | Student Technology Support | N/A | Small | N/A | N/A | Active | Green - On Target, No Risk | Student Life, Student Affairs
105 | 874 |  | C |  |  | Family Business Center would like a Marketplace store to sell tickets and allow people to pay for auction items. Event is Illinois Family Business of the Year Awards gala and silent auction on December 3rd, so they want the store opened as soon as possible. At preliminary meeting, the on-line date was requested to be 11/18/08. |  | Family Business Center would like a Marketplace store to sell tickets and allow people to pay for auction items. Event is Illinois Family Business of the Year Awards gala and silent auction on December 3rd, so they want the store opened as soon as possible. At preliminary meeting, the on-line date was requested to be 11/18/08. | Continuous Service Development | N/A | Small | N/A | N/A | Active | Green - On Target, No Risk | Family Business Center
106 |  |  | C |  |  | Boston College Web Presence at LUC | AJCU Collaboration | No impact on users at LUC. This has impact only on Boston College. On Hold | Continuous Service Development | Q2 | Small | 2008-12-01 | 2008-12-01 | Hold | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
107 |  |  | C |  |  | Phased Implementations: - Gate Review Formalization | Next Phases on PMO, QA, Architecture |  | Continuous Service Development | Q4 | Small | 2007-01-01 | 2009-06-01 | Hold | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
108 |  |  | C |  |  | Phased Implementations: - Change Management, Phase II | Next Phases on PMO, QA, Architecture |  | Continuous Service Development | Q4 | Small | 2007-07-01 | 2009-06-01 | Hold | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
109 |  |  | C |  |  | University Directory Improvements | University Directory Improvements | There is a prevailing need to re-design and/or update the “look and feel” of the current University Directory; from the screen design, to the software used to create the screens, to how the data is gathered and managed. Currently, in order to present information for the University Directory, information is retrieved from several locations and manual processes are executed before the data can be accessed through LUC.EDU. Subsequently, it is difficult to keep this information updated and available in a timely manner. | Continuous Service Development | Q4 | Medium | 2007-10-01 | 2009-06-01 | Hold | Green - On Target, No Risk | Human Resources | 9: Promote a culture of service excellence at all levels.
110 | 376 |  | C |  |  | 1000 students annually participate with Evoke & sponsored events. Access is needed to the students' personal contact, emergency, medical, and demographic data for contact, emergency, and in-house analysis. Also, access to release forms signed by students/staff (media release, release of liability, and medical), and notes fields and past involvement with M&M would like to be saved and tracked. |  | 1000 students annually participate with Evoke & sponsored events. Access is needed to the students' personal contact, emergency, medical, and demographic data for contact, emergency, and in-house analysis. Also, access to release forms signed by students/staff (media release, release of liability, and medical), and notes fields and past involvement with M&M would like to be saved and tracked. | Administrative Initiatives | TBD | Small | TBD | TBD | Hold | Green - On Target, No Risk | Evoke
111 | 449 |  | C |  |  | Request change to application to add one more item to search by. They'd like to add school, which currently is shown next to the city. They'd be removing the school name from that list and puting it in its own category. They have a list of schools ready to populate the drop-down box."This request is not urgent at all, but we'd appreciate it going into the line up of projects in your department." |  | Request change to application to add one more item to search by. They'd like to add school, which currently is shown next to the city. They'd be removing the school name from that list and puting it in its own category. They have a list of schools ready to populate the drop-down box."This request is not urgent at all, but we'd appreciate it going into the line up of projects in your department." | Academic & Faculty Support | TBD | Small | TBD | TBD | Hold | Green - On Target, No Risk | International Studies
112 | 455 |  | C |  |  | Determine if there is a way to notify people when e-mails that are generated by PeopleSoft processes come back as undeliverable. If such a way exists, write the programs or scripts to produce a notification list of all such e-mails. |  | Determine if there is a way to notify people when e-mails that are generated by PeopleSoft processes come back as undeliverable. If such a way exists, write the programs or scripts to produce a notification list of all such e-mails. | Administrative Initiatives | TBD | X-Small | TBD | TBD | Hold | Green - On Target, No Risk | Information Technology Services
113 | 602 |  | C |  |  | Develop or acquire a new Media Services asset and event tracking system. To be used by the Media Services team. This system will be an internal only system and it is desired to be web-based for remote access along with some basic levels of security built-in. Additionally, the tracking of resources such as projectors, laptops, etc. is desired in addition to tracking event data |  | Develop or acquire a new Media Services asset and event tracking system. To be used by the Media Services team. This system will be an internal only system and it is desired to be web-based for remote access along with some basic levels of security built-in. Additionally, the tracking of resources such as projectors, laptops, etc. is desired in addition to tracking event data | Administrative Initiatives | TBD | Small | TBD | TBD | Hold | Green - On Target, No Risk | Information Technology Services
114 | 608 |  | C |  |  | As part of its disaster planning Scott Olivieri at Boston College would like have a single page hosted on our server that they could point to in the event of a campus-wide outage at their site. |  | As part of its disaster planning Scott Olivieri at Boston College would like have a single page hosted on our server that they could point to in the event of a campus-wide outage at their site. | Continuous Service Development | TBD | Small | TBD | TBD | Hold | Green - On Target, No Risk | Information Technology Services
115 | 781 |  | C |  |  | To create an Oracle database that tracks port information for all data jacks in a Residence Hall rooms. |  | To create an Oracle database that tracks port information for all data jacks in a Residence Hall rooms. | Continuous Service Development | TBD | Small | TBD | TBD | Hold | Green - On Target, No Risk | Information Technology Services
116 | 825 |  | C |  | LOCUS Enhancements | Security - Add batch SQR processes which can 1) add user roles from an input file; and 2) add row level security for selected User ID level tables from an input file. |  | Security - Add batch SQR processes which can 1) add user roles from an input file; and 2) add row level security for selected User ID level tables from an input file. | Administrative Initiatives | TBD | Small | TBD | TBD | Hold | Green - On Target, No Risk | Information Technology Services
117 |  |  | C | 2 | Credit Card Processing | Credit Card Processing, Continuing Medical Education | Credit Card Processing |  | Administrative Initiatives | TBD | TBD | TBD | TBD | Hold | Green - On Target, No Risk | Finance | 9: Promote a culture of service excellence at all levels.
118 |  |  | C | 2 | Credit Card Processing | Credit Card Processing, Social Work | Credit Card Processing |  | Administrative Initiatives | TBD | TBD | TBD | TBD | Hold | Green - On Target, No Risk | Finance | 9: Promote a culture of service excellence at all levels.
119 |  |  | C | 2 | Credit Card Processing | Credit Card Processing, SSOM Ministry | Credit Card Processing |  | Administrative Initiatives | TBD | TBD | TBD | TBD | Hold | Green - On Target, No Risk | Finance | 9: Promote a culture of service excellence at all levels.
120 | 732 |  | C |  |  | Update the current software request form http://orpheus.it.luc.edu/infotech/icomp/swreq.cfm with a new form. The old one is very outdated; additional and different information now needs to be collected. |  | Accurately and efficiently gather faculty requests for software to be installed in computer labs. | Academic & Faculty Support | Q3 | Small | TBD | TBD | Hold | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
121 | 626 |  | C |  |  | Resident Parking Lottery Application enhancements |  | Enhancements to Resident Parking Lottery Appl. The initial appl. request was to have a form site for students to apply for access to a parking lot, and an admin site to run a lottery to choose winners for the parking lots based on students' dorm assignment. Enhancement requests include allowing multiple runs of the lottery with different student dorm to parking lot associations. | Academic & Faculty Support | Q3 | Small | TBD | TBD | Hold | Green - On Target, No Risk | FN-Parking/Business Services | 9: Promote a culture of service excellence at all levels.
122 | 656 |  | C |  |  | Enhancements to SCPS Continuum web site - Phase II enhancements |  |  | Academic & Faculty Support | Q4 | Large | 2007-06-01 | TBD | Hold | Green - On Target, No Risk | AA-Colleges & Schools | 2: Increase its overall student enrollment at the undergraduate and graduate levels through the development of new academic programs.
123 | 541 |  | C |  |  | Provide integrated logon for all Faculty Information Systems modules |  | Single-sign-on for all Faculty Information Systems modules | Continuous Service Development | Q3 | Medium | 2008-02-01 | TBD | Hold | Green - On Target, No Risk | AA-Faculty Administration | 9: Promote a culture of service excellence at all levels.
124 | 542 |  | C |  |  | Reformat existing Faculty Information System Modules 1&2 pages to match the updated pages used in the Faculty Development module. |  | Reformat existing Faculty Information System Modules 1&2 pages to match the updated pages used in the Faculty Development module. | Continuous Service Development | Q3 | Medium | 2008-02-01 | TBD | Hold | Green - On Target, No Risk | AA-Faculty Administration | 9: Promote a culture of service excellence at all levels.
125 | 268 |  | C | 6 | “Housing / Scheduling” Projects | Expansion of Sullivan Ctr Scheduling Solution (TimeTrade) |  | Expansion of Sullivan Ctr Scheduling | Academic & Faculty Support | TBD | TBD | 2007-07-07 | TBD | Hold | Green - On Target, No Risk | AA-Office of the Provost | 9: Promote a culture of service excellence at all levels.
126 | 872 |  | C |  | LOCUS Enhancements | Improve class search for cross-listed non-enrollment classes in LOCUS. |  |  | Student Technology Support | Q3 | Small | 2008-12-01 | 2009-01-01 | Pending | Green - On Target, No Risk | AA-Registration & Records
127 | 754 |  | C | 2 | Credit Card Processing | Credit Card Processing for Gift Shop for LUMA |  | Credit Card Processing | Administrative Initiatives | Q4 | Medium | 2009-04-01 | 2009-05-01 | Pending | Green - On Target, No Risk | Finance | 9: Promote a culture of service excellence at all levels.
128 |  |  | C |  |  | Phased Implementations: - Change Management, Metrics & Improvements |  | Next Phases on PMO, QA, Architecture | Continuous Service Development | Q4 | Medium | 2009-03-01 | 2009-06-01 | Pending | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
129 |  |  | C |  |  | Phased Implementations: - Project Management Methodology, Metrics & Improvements |  | Next Phases on PMO, QA, Architecture | Continuous Service Development | Q1 | Medium | 2009-02-01 | 2009-08-01 | Pending | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
130 | 857 |  | C |  |  | Website for reporting racial bias/prejudice incidents. |  | A confidential web site will provide a place for anyone to report an incident anononmously. These reportings would be sent immediately to appropriate staff to be investigated | Academic & Faculty Support | Q3 | Small | TBD | TBD | Pending | Green - On Target, No Risk | Finance | 9: Promote a culture of service excellence at all levels.
131 | 133 |  | C |  |  | Electronic Lockbox - Interface with Bank One for the processing of electronic tuition payments from student/parent accounts with Bank One or other banks, for deposit to Loyola's account at Bank One. Bank One would make a daily payment file available for download from their website, probably in the same way that they now provide a file of "normal" (paper checks, via U.S. mail) lockbox payments. |  | Electronic Lockbox - Interface with Bank One for the processing of electronic tuition payments from student/parent accounts with Bank One or other banks, for deposit to Loyola's account at Bank One. Bank One would make a daily payment file available for download from their website, probably in the same way that they now provide a file of "normal" (paper checks, via U.S. mail) lockbox payments. | Administrative Initiatives | TBD | Small | TBD | TBD | Pending | Green - On Target, No Risk | Treasurer
132 | 852 |  | C |  |  | Devise and implement a procedure to automatically create special security allowances for a select group of people within the CS90PRE environment that will take effect after each weekly refresh from production. |  | Devise and implement a procedure to automatically create special security allowances for a select group of people within the CS90PRE environment that will take effect after each weekly refresh from production. | Administrative Initiatives | TBD | X-Small | TBD | TBD | Pending | Green - On Target, No Risk | Information Technology Services
133 |  | R | C |  |  | Loyola Alert - Phase II | Loyola Alert - Phase II | Determine enhancements to Phase I rollout and if registration will be required. | Infrastructure | TBD | TBD | TBD | TBD | Pending | Green - On Target, No Risk | Facilities | 3: Enhance the quality of campus life for resident and commuter students.
134 | 719 |  | C |  |  | This is a request to enhance the functionality within PSS. It is desired to have the capability to identify relationships between related projects ie a Parent-Child relationship. This will allow the grouping of these projects. As an example we have several projects that are being implemented via the TouchNet Marketplace tool. |  |  | Continuous Service Development | Q3 | Small | TBD | TBD | Pending | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
135 | 803 | R | C | 9 | Student Experience/Portal Improvements | Current students portal enhancements | Student Experience/Portal Improvements | Current students Portal Enhancements. Project intended to support goal of increasing retention and enhanced service to current students. Objective is to improve sudent access to the information they need in an efficient, convenient and appealing way. It is intended that students will transistion from the "Admitted Students" portal thie current students portal. | Student Technology Support | Q2 | Large | TBD | TBD | Pending | Green - On Target, No Risk | AA-Enrollment Management | 2: Increase its overall student enrollment at the undergraduate and graduate levels through the development of new academic programs.
136 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Lawson Lot (YMCA) | Campus Construction Initiatives (15) | Mandated. In support of administration and facilities initiatives. | Infrastructure | Q3 | Small | 2008-09-01 | 2009-01-01 | Active | Green - On Target, No Risk | Facilities
137 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Burrowes House for Provost and President | Campus Construction Initiatives (15) | Remodel the old Yellow house. | Infrastructure | Q3 | Medium | 2008-09-01 | 2009-03-01 | Active | Green - On Target, No Risk | Facilities
138 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Remodel Terry Center | Campus Construction Initiatives (15) | Mandated. In support of administration and facilities initiatives. | Infrastructure | Q3 | Medium | 2008-12-01 | 2009-03-01 | Active | Green - On Target, No Risk | Facilities
139 |  | R | M | 4 | Construction Projects | WTC Data Center Remediation | WTC Data Center Assessment | Current data center lacks proper environmental services. This project will address required cooling and power needs. Temporary resolution approved and started. | Infrastructure | Q4 | Large | 2007-10-01 | 2009-06-01 | Active | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
140 |  |  | M | 5 | Security Projects | PCI/DSS Compliance | Security Initiatives (PIRG & Audit Related) | Compliance to the PCI/DSS standard is mandatory. Failure to comply with the standard can result in significant fines and a critical risk from a PR perspective. Additionally, if a breach of credit card data occurs while Loyola is non-compliant, Loyola would be forced to comply as a Level 1 merchant in addition to a multitude of additional fines. Total costs for such noncompliance or a breach could be significant. | Continuous Service Development | Q4 | X-Large | 2008-03-01 | 2009-06-01 | Active | Yellow - Target in Jeopardy, Risks Being Managed, Unknowns Exist | Finance | 9: Promote a culture of service excellence at all levels.
141 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Coffey Hall remodeling | Campus Construction Initiatives (15) | Entire building being remodeled | Infrastructure | Q4+ | Large | 2008-04-01 | 2009-07-01 | Active | Green - On Target, No Risk | Facilities
142 |  |  | M | 4 | Construction Projects | Construction Initiatives: - 20-24 Chicago Ave. | Campus Construction Initiatives (15) | New building on Chicago Avenue attached to 25 E | Infrastructure | Q4+ | Large | 2008-05-01 | 2009-08-01 | Active | Green - On Target, No Risk | Facilities
143 |  | R | M | 4 | Construction Projects | Construction Initiatives: - Mundelein – Infrastructure Design & Implementation Multi - phased. | Campus Construction Initiatives (15) | Mandated. In support of academic and facilities initiatives. | Infrastructure | Q4+ | Large | 2007-01-01 | 2009-12-01 | Active | Green - On Target, No Risk | Facilities
144 |  |  | M | 4 | Construction Projects | Construction Initiatives: - 25 E law School Multi phased | Campus Construction Initiatives (15) | Lewis Library and Law School Library are switching locations | Infrastructure | Q4+ | Large | 2008-04-01 | 2010-07-01 | Active | Green - On Target, No Risk | Facilities
145 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Crown Center Lower level | Campus Construction Initiatives (15) | Upon relocation of servers remodel space for modern languages | Infrastructure | Q4+ | Medium | 2008-07-01 | 2009-06-01 | Pending | Green - On Target, No Risk | Facilities
146 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Sullivan Center | Campus Construction Initiatives (15) | CAS to Sullivan | Infrastructure | Q4+ | Small | 2008-07-01 | 2009-06-01 | Pending | Green - On Target, No Risk | Facilities
147 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Granada Center | Campus Construction Initiatives (15) | School of Nursing to Granada | Infrastructure | Q4+ | Medium | 2008-07-01 | 2009-06-01 | Pending | Green - On Target, No Risk | Facilities
148 |  |  | M | 4 | Construction Projects | Construction Initiatives: - VSTC | Campus Construction Initiatives (15) | Addition on to Gentile for Varsity sports | Infrastructure | Q4+ | Medium | 2008-05-01 | 2009-07-01 | Pending | Green - On Target, No Risk | Facilities
149 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Faculty / Staff lounge | Campus Construction Initiatives (15) | New faculty staff lounge adjacent to Cudahy Science | Infrastructure | Q4+ | Medium | 2008-05-01 | 2009-07-01 | Pending | Green - On Target, No Risk | Facilities
150 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Damen Hall | Campus Construction Initiatives (15) | Prepare for the razing of Damen Hall | Infrastructure | Q4+ | Large | 2009-09-01 | TBD | Pending | Green - On Target, No Risk | Facilities
151 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Mundelein | Campus Construction Initiatives (15) | Implement and academic server area adjacent to existing data room in lower level | Infrastructure | Q4+ | Medium | 2009-04-01 | TBD | Pending | Green - On Target, No Risk | Facilities

## FY09 Q1-Q2 Completed
[6 empty] | Plan of Record Data - Key Fields |  |  |  |  | Plan of Record Data - New Fields
67
Row Nbr | PSS Nbr | Level | Priority | Program Number | Program Group Name | Project Desc | Major Initiative/Ring Desc | Institutional Impact Statement | Strategic Category | Est. Compl. (QTR) | T-Shirt Sizing | Targeted Start Month (MM/YYYY) | Targeted Finish Month (MM/YYYY) | Status | Primary Customer | Goal Alignment
152 | 739 | R | A | 1 | Student System Upgrade | Upgrade RDS to PeopleSoft 9.0 Tables The RDS will be upgraded to extract data from PeopleSoft 9.0. | Student System Upgrade | Maintain functionality of the student reporting database (RDS) after LOCUS upgrade until a more permanent solution is implemented. | Academic & Faculty Support | Q1 | Medium | 2007-10-31 | 2008-07-01 | Complete | Academic Affairs | 5: Improve the academic quality of incoming students and academic programs.
153 | 667 | R | A | 1 | Student System Upgrade | LOCUS Campus Solutions 9.0 upgrade | Student System Upgrade | Continuation of support and regulatory updates for LOCUS after current support ends on 8/31/2007. Required step of the SIS upgrade. | Academic & Faculty Support | Q1 | X-Large | 2007-05-01 | 2008-07-01 | Complete | AA-Office of the Provost | 3: Enhance the quality of campus life for resident and commuter students.
154 | 32 | R | A | 3 | LOCUS Enhancements | Implement collections module within the student system | LOCUS Enhancements (16) | Currently the Busar staff use excel list from the Collectors report.Any updates to a student account are done manually. Utilization of the Collectors Module should streamline the process, improve workflow and communication with staff.Bottom line impact should be a reduced accounts receivables and fewer acctounts turned over to collection agencys | Administrative Initiatives | Q1 | Small | 2008-06-01 | 2008-08-01 | Complete | Finance | 9: Promote a culture of service excellence at all levels.
155 |  | R | A |  |  | Residential Wireless _ SLLC | Wireless Expansion | Install wireless connectivty to SLLC | Infrastructure | Q1 | Large | 2008-05-01 | 2008-08-01 | Complete | Student Affairs
156 |  | R | A | 5 | Security Projects | Personal Information Risk Group (PIRG) Policy Implementation | Security Initiatives (PIRG & Audit Related) | Create and implement the required policies, supporting procedures and training to protect and govern personally identifiable information (PII). The policies and processes are required to enable institutional governance. Not implementing will result in an increased risk to the unwanted exposure of PII. | Continuous Service Development | Q1 | Large | 2006-09-01 | 2008-09-01 | Complete | Office of the President | 9: Promote a culture of service excellence at all levels.
157 |  | R | A |  |  | Relocate Servers from Crown | Relocate Servers from Crown | Complete move of servers from Crown Center data center to new Dumbach data center to make way for new classrooms required in Crown Center space. | Infrastructure | Q1 | Large | 2008-08-01 | 2008-09-01 | Complete | Information Technology Services
158 | 782 | R | A |  |  | BOT web site | Board of Trustees Web Site | Provide site for Father Garanzini and the Board of Trustees to use for collaboration, such as the sharing of assorted documentation and communications. It should be accessible via LDAP authentication. | Administrative Initiatives | Q1 | Medium | 2008-04-01 | 2008-09-01 | Complete | Office of the President | 9: Promote a culture of service excellence at all levels.
159 |  |  | A |  |  | Centralized Policies and Procedures Web Site |  | A centralized web site will provide a single place for users of Loyola's web pages to locate current departmental policies and procedures. Should cut down on inquiries as well as increase the efficiency of updates. | Administrative Initiatives | Q1 | Small | 2008-07-01 | 2008-09-01 | Complete | Finance
160 | 635 | R | A | 8 | Advancement | Upgrade Advancement databases to 10g | BSR/Smartcall Upgrade | Required first step to upgrade the Advancement application (see PSS 325,339). Additionally, the upgrade of the database to 10g provides more robust database tools fr performance tuning and maintenance. | Administrative Initiatives | Q2 | Medium | 2008-02-01 | 2008-10-01 | Complete | Advancement | 10: Enhance its development efforts and alumni engagement.
161 | 325, 339 | R | A | 8 | Advancement | Upgrade BSR/SmartCall to new release | BSR/Smartcall Upgrade | New functions allow gathering more specific information on donors so as to better target fund raising efforts. Security of the application is greatly enhanced. Additional functionality in the areas of Cell Phone Management, Allocation Tracking, Gift Processing, Email address consolidation and provides the ability to have release note access | Administrative Initiatives | Q2 | Large | 2007-05-01 | 2008-10-01 | Complete | Advancement | 10: Enhance its development efforts and alumni engagement.
162 | 463 | R | A |  |  | Import Bio-Demo data into Campus Card to update cardholder records | Import Bio-Demo Data into Campus Card | Import Bio-Demo data into Campus Card to update cardholder records | Administrative Initiatives | Q2 | X-Small | 2008-09-01 | 2008-10-01 | Complete | Finance | 9: Promote a culture of service excellence at all levels.
163 | 794 | R | A | 2 | Credit Card Processing | Convert CC usage of UGRAD admissions from Touchnet API to UPAY | Convert Undergrad Credit Card Usage to UPAY | PCI Compliance Concern - Convert Undergraduate Admissions' acceptance of credit card payments for Admission Deposits and Housing Deposits to UPay from the older TouchNet JSP API which runs in-house on our Orpheus server. UPay is easier to audit for PCI compliance, and is hosted by TouchNet. This UA credit card acceptance application is the last one at LUC using the JSP API. | Administrative Initiatives | Q2 | Small | 2008-05-01 | 2008-11-01 | Complete | AA-Office of the Provost | 9: Promote a culture of service excellence at all levels.
164 |  | R | A | 9 | Student Experience/Portal Improvements | create UVIDs for incoming Freshmen earlier in the process (Admissions request) This project is tied to the Admitted Students Portal | Student Experience/Portal Improvements | Create a website/portal exclusively for newly admitted students to provide custom information in an easily accessible and “exclusive” site, offering a more personalized and community-based online experience to admitted students. We believe this more contemporary content delivery method will engage admitted students with Loyola earlier and allow them to make connections with other students with similar interests during the admissions process. | Student Technology Support | Q2 | Large | 2008-01-01 | 2008-11-01 | Complete | AA-Enrollment Management | 2: Increase its overall student enrollment at the undergraduate and graduate levels through the development of new academic programs.
165 | 762 | R | A |  |  | Messaging and Information Lists | Messaging and Information Lists | There is a need to be able to easily create email lists for targeted groups such as faculty, staff or students taking into consideration each individuals status and then sending the email. Consideration must be given to the abiliy to break these groups down into smaller targeted groups such as: 'all currently enrolled students in the business school that live in the residence halls' or 'all full time faculty'. This capability will enable the proper delivery of special broadcasts and targeted communications to communicate to the right person at the right place at the right time and in the right manner. | Continuous Service Development | Q2 | Medium | 2008-01-01 | 2008-11-01 | Complete | Marketing & Communication | 9: Promote a culture of service excellence at all levels.
166 | 860 |  | A |  |  | Strategic Planning Committee web site |  | Provide a web site dedicated to use by the Strategic Planning Committee, including wikis, possibly blogs, as the develop and share the work of the committee. Provide LDAP authentication, and various levels of security access. | Administrative Initiatives | Q2 | Small | 2008-10-01 | 2008-11-01 | Complete | Office of the President
167 | 320 | R | A | 3 | LOCUS Enhancements | LOCUS Enhancements: - Self Service Apply for Graduation | LOCUS Enhancements (16) | Unify disparate school graduation applications to support self service for students applying for graduation. | Academic & Faculty Support | Q2 | Small | 2007-04-01 | 2008-12-01 | Complete | AA-Registration & Records | 9: Promote a culture of service excellence at all levels.
168 | 727 | R | A | 3 | LOCUS Enhancements | A report that shows the results of each night's Tuition Calculation results. | LOCUS Enhancements (16) | Report used to identify students that are charged incorrectly, will eliminate student complaints | Academic & Faculty Support | Q2 | Small | 2008-11-05 | 2008-12-01 | Complete | General Accounting | 9: Promote a culture of service excellence at all levels.
169 | 568 | R | A | 3 | LOCUS Enhancements | Debug Account Audit Statement | LOCUS Enhancements (16) | Improve useability of Account Audit Statement report. | Administrative Initiatives | Q2 | Large | 2008-08-01 | 2008-12-01 | Complete | Finance | 9: Promote a culture of service excellence at all levels.
170 | 798 | R | A | 9 | Student Experience/Portal Improvements | Admitted Students Portal | Student Experience/Portal Improvements | Create a website/portal exclusively for newly admitted students to provide custom information in an easily accessible and “exclusive” site, offering a more personalized and community-based online experience to admitted students. We believe this more contemporary content delivery method will engage admitted students with Loyola earlier and allow them to make connections with other students with similar interests during the admissions process. | Student Technology Support | Q2 | Large | 2008-05-01 | 2008-12-01 | Complete | AA-Enrollment Management | 2: Increase its overall student enrollment at the undergraduate and graduate levels through the development of new academic programs.
171 | 802 | R | A |  |  | Update to the self-service module of the EMR Point & Click solution and complete the required production reporting for the Wellness Center. | Wellness Electronic Medical Records - Self Service | Added efficiencies for student self service and required operational reporting. | Student Technology Support | Q2 | Medium | 2007-11-01 | 2008-12-01 | Complete | Student Affairs | 3: Enhance the quality of campus life for resident and commuter students.
172 | 709 | R | A |  |  | This is the next phase of IDM3. The immediate need is to provide SSOM University employees the ability to authenticate to University resources to administer their own benefits. The secondary need is to uniquely identify all Loyola employees (Hospital and University) so that we might identify and use the same UVID on either side of Loyola. The SST stands for Shared Source of Truth. | LDAP Authentication with LUMC (IDM3 Phase II) | Provide a share database that will allow LUMC and LUC to verify uvid, reducing redundancy and conflicts. Provides a method to streamline access to shared resources. | Administrative Initiatives | Q2 | Large | 2007-06-01 | 2008-12-01 | Complete | Human Resources | 8: Strengthen it relationship with the City of Chicago and the neighborhoods of the Water Tower, Lake Shore and Medical Center Campuses.
173 | 866 |  | A |  |  | Enhancements to Budget Application System |  |  | Administrative Initiatives | Q2 | Medium | 2008-10-01 | 2008-12-01 | Complete | Finance | 9: Promote a culture of service excellence at all levels.
174 | 734 |  | B | 5 | Security Projects | Secure all Oracle bkup directories on all Oracle servers. | Security Initiatives (PIRG & Audit Related) | Secure databases from internal and external attacks | Infrastructure | Q1 | Small | 2008-06-01 | 2008-07-01 | Complete | Information Technology Services | 9: Promote a culture of service excellence at all levels.
175 |  |  | B |  |  | Upgrade Technology in Provost's Office @ WTC | Provost's Office Conference Room Upgrade | In support of academic and facilities initiatives, ITS coordinates, installs, and supports new classrooms, conference rooms, and other spaces defined in construction projects. | Continuous Service Development | Q1 | X-Small | 2008-06-01 | 2008-07-01 | Complete | Academic Affairs
176 |  |  | B |  |  | Develop, deploy and evaluate two pilots for online teacher course evaluation processes using commercial products | Develop, deploy and evaluate pilots for online teacher course evaluation processes |  | Academic & Faculty Support | Q1 | Medium | 2007-11-01 | 2008-07-01 | Complete | Academic Affairs
177 |  | R | B |  |  | Pilot Rich Media Offerings (Podcasting, Blog/Wiki, Video Streaming) | Pilot Rich Media Offerings (Podcasting, Blog/Wiki, Video Streaming) |  | Continuous Service Development | Q1 | Medium | 2008-01-01 | 2008-07-01 | Complete | Academic Affairs | 5: Improve the academic quality of incoming students and academic programs.
178 |  |  | B |  |  | Upgrade Technology in Simpsom MPR | Simpsom MPR Refresh | In support of academic and facilities initiatives, ITS coordinates, installs, and supports new classrooms, conference rooms, and other spaces defined in construction projects. | Continuous Service Development | Q1 | Small | 2008-06-01 | 2008-07-01 | Complete | Academic Affairs
179 | 742 | R | B |  |  | Modify the Convio to BSR interface to accomodate the addition of gifts being made through the Convio web site. | Convio to BSR Interface | Modify the Convio to BSR interface to accomodate the addition of gifts being made through the Convio web site. | Administrative Initiatives | Q1 | Medium | 2007-11-01 | 2008-07-01 | Complete | Advancement | 10: Enhance its development efforts and alumni engagement.
180 |  |  | B |  |  | Upgrade Group Study & Equipment Reservation System(s) | Upgrade Group Study & Equipment Reservation System(s) |  | Administrative Initiatives | Q1 | Small | 2008-06-01 | 2008-08-01 | Complete | Information Technology Services | 6: Promote multidisciplinary collaborations.
181 |  |  | B |  |  | Expand Equipment Loan Program with additional online training and equipment available through AT&T Grant | Expansion of Digital Media Equipment Loan Program |  | Continuous Service Development | Q1 | Medium | 2008-06-01 | 2008-08-01 | Complete | AA-Colleges & Schools | 7: Expand its investment in research and scholarship in order to take full advantage of its academic strengths.
182 |  | R | B |  |  | Pilot Rich Media Offerings (Podcasting, Blog/Wiki, Video Streaming) | Pilot Rich Media Offerings (Podcasting, Blog/Wiki, Video Streaming) |  | Continuous Service Development | Q1 | Large | 2008-01-01 | 2008-08-01 | Complete | Academic Affairs
183 |  |  | B |  |  | Network Initiative - Damen Hall | Network Enhacement | upgrade the network infrastructure in the closets | Infrastructure | Q1 | Small | 2008-04-01 | 2008-08-01 | Complete | Information Technology Services
184 |  |  | B |  |  | Phase II of Call Tracking System Implementation | Call Tracking Self Service |  | Continuous Service Development | Q1 | Medium | 2008-01-01 | 2008-09-01 | Complete | Information Technology Services | 9: Promote a culture of service excellence at all levels.
185 |  |  | B |  |  | Develop support model proposal and update budget plan for current technology in the Information Commons | Enhance Information Commons Service Offerring |  | Continuous Service Development | Q1 | Small | 2008-05-01 | 2008-09-01 | Complete | Academic Affairs
186 |  | R | B |  |  | Academic Wireless - Flanner & LSB | Wireless Expansion | Expansion of wireless. Strengthens Loyola's competitiveness | Student Technology Support | Q1 | Large | 2008-01-01 | 2008-09-08 | Complete | Academic Affairs | 1: Enrich its rigorous academic programs to better integrate the unique strengths and characteristics of a Jesuit and Catholic education.
187 |  |  | B |  |  | Build plan and timeline proposal for In-sourced Blackboard learning System | Build plan and timeline proposal for In-sourced Blackboard learning System |  | Academic & Faculty Support | Q2 | Large | 2008-04-01 | 2008-10-01 | Complete | Academic Affairs | 1: Enrich its rigorous academic programs to better integrate the unique strengths and characteristics of a Jesuit and Catholic education.
188 |  |  | B |  |  | Transition from "Call Track" system to HEAT for ResNet support application | ResNet System Replacement |  | Continuous Service Development | Q2 | Medium | 2008-04-01 | 2008-10-01 | Complete | Academic Affairs
189 | 821 |  | B | 2 | Credit Card Processing | Credit Card Processing, Executive Education | Credit Card Processing |  | Administrative Initiatives | Q2 | Medium | 2008-09-01 | 2008-11-01 | Complete | Finance | 9: Promote a culture of service excellence at all levels.
190 | 788 | R | B |  |  | Entrance Control for Gentile Center | Entrance Control for Gentile Center | This project has changed from building a small cabability to a purchase of a hosted ticket application that handles season ticket holders and students | Administrative Initiatives | Q2 | Small | 2008-04-01 | 2008-11-01 | Complete | Student Affairs | 9: Promote a culture of service excellence at all levels.
191 |  |  | B |  |  | iHeat - provides access to Heat call logging(including First level support) | Provides access to Heat Call logging |  | Continuous Service Development | Q2 | Medium | 2008-06-01 | 2008-11-01 | Complete | Academic Affairs | 9: Promote a culture of service excellence at all levels.
192 |  |  | B |  |  | iHeat - provides access to Heat call logging(including First level support) | Provides access to Heat Call logging |  | Continuous Service Development | Q2 | Medium | 2008-08-01 | 2008-11-01 | Complete | Academic Affairs
193 | 690 |  | B | 2 | Credit Card Processing | Credit Card Processing, Preschool Tuition Payment | Credit Card Processing |  | Administrative Initiatives | Q2 | Medium | 2008-09-01 | 2008-12-01 | Complete | Finance | 9: Promote a culture of service excellence at all levels.
194 | 714 | R | B | 3 | LOCUS Enhancements | When a staff member enters direct deposit information for a student, they can use effective dated rows and an inactive/active status flag to track the history of a student's direct deposit account changes. But then students manage their own direct deposit information via self-service, there is no effective dating - they overwrite their previous information. | LOCUS Enhancements (16) |  | Administrative Initiatives | Q2 | Large | 2008-01-01 | 2008-12-01 | Complete | Office Of The Bursar | 9: Promote a culture of service excellence at all levels.
195 |  |  | B |  |  | New Technology Testing (Vista, Office 2007, Share Point) | New Technology Testing (Vista, Office 2007, Share Point) | Determine how these technologies will fit in our environment. Plans to deploy Office 2007 in labs Fall08 | Continuous Service Development | Q2 | Medium | 2008-06-07 | 2008-12-01 | Complete | Information Technology Services | 9: Promote a culture of service excellence at all levels.
196 | 736 |  | B |  |  | Mismatch SSN between Lawson and PS--Create Reports and views that can help HR(Carol McCormack) and Student Admin (Kris Dagget) resolve SSN discrepancies between LOCUS and Lawson. |  | Mismatch SSN between Lawson and PS- Create Reports and views that will coordinate the resolving issues between HR and PS | Administrative Initiatives | Q2 | Small | 2008-06-01 | 2008-12-08 | Complete | Information Technology Services | 9: Promote a culture of service excellence at all levels.
197 |  |  | C |  |  | Improve Spam Detection | Reduction in SPAM | We currently have a spam detection system in place. This project is to enhance the current system by installing appliances to further reduce SPAM. | Continuous Service Development | Q1 | Large | 2008-05-01 | 2008-09-01 | Complete | Information Technology Services | 9: Promote a culture of service excellence at all levels.
198 |  |  | C |  |  | Leopard OS Testing |  | Continue to integrate Mac platforms into our environment | Infrastructure | Q1 | Medium | 2008-01-08 | 2008-09-01 | Complete | Information Technology Services
199 |  |  | C |  |  | Phased Implementations: - Quality Assurance Methodology, pilot projects and begin training | Next Phases on PMO, QA, Architecture |  | Continuous Service Development | Q1 | Small | 2008-01-01 | 2008-09-01 | Complete | Information Technology Services | 9: Promote a culture of service excellence at all levels.
200 | 806 |  | C | 2 | Credit Card Processing | Credit Card Processing, Bioethics | Credit Card Processing |  | Administrative Initiatives | Q2 | Small | 2008-09-01 | 2008-11-01 | Complete | Finance | 9: Promote a culture of service excellence at all levels.
201 | 867 |  | C | 2 | Credit Card Processing | Credit Card Processing, Graduate School of Business Study Abroad Trips | Credit Card Processing |  | Administrative Initiatives | Q2 | Small | 2008-11-01 | 2008-11-01 | Complete | Finance | 9: Promote a culture of service excellence at all levels.
202 | 822 |  | C | 2 | Credit Card Processing | Credit Card Processing, Health Law and Policy | Credit Card Processing |  | Administrative Initiatives | Q2 | Small | 2008-08-01 | 2008-12-01 | Complete | Finance | 9: Promote a culture of service excellence at all levels.
203 | 433 | R | C | 3 | LOCUS Enhancements | LOCUS Enhancements: - Change the transcript level default on the entry of transfer credit to "Official". The current default is "Unofficial" and does not print the summary on the official transcript. | LOCUS Enhancements (16) |  | Academic & Faculty Support | Q2 | Small | 2006-07-01 | 2008-12-01 | Complete | AA-Registration & Records | 5: Improve the academic quality of incoming students and academic programs.
204 | 870 |  | C | 3 | LOCUS Enhancements | Changing minors/second majors from suplans to plans. |  |  | Academic & Faculty Support | Q2 | Small | 2008-11-01 | 2008-12-01 | Complete | AA-Registration & Records
205 |  | R | M | 4 | Construction Projects | Construction Initiatives: - Ignatius House | Campus Construction Initiatives (22) | Mandated. In support of facilities initiatives. | Infrastructure | Q1 | Large | 2008-01-01 | 2008-07-01 | Complete | Facilities
206 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Cudahy Library | Campus Construction Initiatives (22) | Install wireless connectivty to Echo Room | Infrastructure | Q1 | Small | 2008-05-01 | 2008-07-01 | Complete | Facilities
207 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Crown Center | Campus Construction Initiatives (22) | Remodel CC 114/115 to an Electroinc classroom only | Infrastructure | Q1 | Small | 2008-05-01 | 2008-07-01 | Complete | Facilities
208 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Sullivan Center | Campus Construction Initiatives (22) | Remodeling and moving of staff in Sullivan center | Infrastructure | Q1 | Small | 2008-05-01 | 2008-07-01 | Complete | Facilities
209 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Bus Shelter | Campus Construction Initiatives (22) | Equip new bus shelter with technology | Infrastructure | Q1 | Small | 2008-05-01 | 2008-07-01 | Complete | Facilities
210 |  |  | M |  |  | Create Electronic space in Echo Room of Cudahy Library | Cudahy Library Echo Room Technology | In support of academic and facilities initiatives, ITS coordinates, installs, and supports new classrooms, conference rooms, and other spaces defined in construction projects. | Continuous Service Development | Q1 | Small | 2008-05-01 | 2008-07-01 | Complete | Academic Affairs
211 |  | R | M | 4 | Construction Projects | Construction Initiatives: - Santa Clara Remodeling | Campus Construction Initiatives (22) | Mandated. In support of academic and facilities initiatives. | Infrastructure | Q1 | Large | 2007-05-01 | 2008-08-01 | Complete | Facilities
212 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Sullivan Center | Campus Construction Initiatives (22) | Equip Galvin Auditorium with technology | Infrastructure | Q1 | Small | 2008-04-01 | 2008-08-01 | Complete | Facilities
213 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Mertz Hall | Campus Construction Initiatives (22) | Remodel old east west lounge for staff | Infrastructure | Q1 | Small | 2008-05-01 | 2008-08-01 | Complete | Facilities
214 |  |  | M |  |  | Security Initiative | Safety for on campus | Implement a Wide area emergency broadcast system via an announcement to emergency phones strategically locate4d on campus | Student Technology Support | Q1 | Small | 2008-04-01 | 2008-08-01 | Complete | Facilities
215 |  | R | M | 4 | Construction Projects | Construction Initiatives: - New Dorm's online - Le Moyne, Canisius at LSC | Campus Construction Initiatives (22) | Mandated. In support of academic and facilities initiatives. | Infrastructure | Q1 | Large | 2008-05-01 | 2008-08-08 | Complete | Facilities
216 |  |  | M |  |  | Provide Technology in LUMA @ WTC | LUMA Technology | In support of academic and facilities initiatives, ITS coordinates, installs, and supports new classrooms, conference rooms, and other spaces defined in construction projects. | Continuous Service Development | Q1 | Small | 2008-04-01 | 2008-09-01 | Complete | Academic Affairs
217 |  | R | M |  |  | Create Electronic space on 4th Floor of Information Commons | Information Commons Improvements | In support of academic and facilities initiatives, ITS coordinates, installs, and supports new classrooms, conference rooms, and other spaces defined in construction projects. | Continuous Service Development | Q2 | Medium | 2008-06-01 | 2008-11-01 | Complete | Academic Affairs
218 |  | R | M | 4 | Construction Projects | Construction Initiatives: - The Clare - Infrastructure Design and Budgeting | Campus Construction Initiatives (22) | Mandated. In support of academic and facilities initiatives. | Infrastructure | Q2 | Large | 2006-10-01 | 2008-12-01 | Complete | Facilities