## Overview
Loyola University Chicago
ITS Project Document Checklist Guide
Project Initiation
Document Purpose
The project document checklist helps users identify the suggested documentation for their project based on:
· What's the duration and scope of the project, how many people are involved, what's the project budget, etc?
· How do you want to communicate the status of the project, what's outstanding, and who's doing what. What documents should you use?
· It is the decision of the Sponsor and PM/Lead to determine what types of project documentation provide a "best fit" approach for their needs.
· It is suggested to include this completed document in your project folder as your first step in identifying your project documentation needs.
Instructions
· On the next tab, Complete the questionnaire
· At the bottom of the next tab, review the project documentation suggestions.
· For clarification of terms, copies of documentation, or additional info, use the Project Resource Tab for more information.
· If needed, print a copy of the results for your project discussion with your sponsor (each page is set-up to be Print-ready).
· Confirm with your project sponsor what level of documentation is needed, for your project and document it in the Scope as PM Deliverables.
· List any documents the Sponsor decided were not necessary and why, to learn how adjustments are made to recommended documentation.
· Save a copy of this document in your project folder.
When to use this document
· Projects that have been assigned to the ITS Plan of Record, and can be run by the designated Lead or PM for a project
· Unscheduled projects that become part of the Plan of Record
· Projects that are assigned in the PSS as Project Type = "Upgrade", or "Service Request", or "Regulatory", or "Report"
· Projects are unique, temporary endeavors, undertaken to create a unique product or service.
· ELT FTE Planning Project definition: a) Projects & Delivery - Targeted Effort With Fixed Scope, Time and Deliverables, Designing and Building Systems/Solutions/Software/Hardware, Running Projects, Business Analysis, Testing
When NOT to use this document
· Any work that is accounted for outside of the PSS System
· Projects that HAVE NOT been assigned to the ITS Plan of Record or unscheduled projects that will not become part of the Plan of Record
· Projects that are assigned in the PSS as Project Type = "Ongoing"
· ELT FTE Planning non-Project definition: a) Administration & Development - Vacation, Sick, Out of Office, Management of Staff, Staff Meetings, Email, Training, Conferences, Seminars b) Support & Operations - Operational/Ongoing Work and Services, Maintenance, Routine Upgrades, Break & Fix, Troubleshooting, Bug Fixing, Compliance, Audit & Risk, System Administration
Next Page

## Questionnaire
ITS Project Document Checklist
Today's Date
Project Name
PSS # (if assigned)
Project Manager / Lead
CAVEAT: You MUST answer all the questions to receive the document suggestions at the bottom.
Primary Questions |  | Example | Select One Drop-Down Answer Per Line:
What is the duration of this project based on the Project Start date through the Project End date? |  | ⓘ
Will this project increase or create any NEW capital or operating expenditures? |  | ⓘ
How many people will be impacted (directly and indirectly) by this project's final deliverable? |  | ⓘ
Secondary Questions
How many VPs are involved with your project? |  | ⓘ
Has this project been approved through the Plan of Record? |  | ⓘ
How many leads are on this project? |  | ⓘ
What is the perceived level of risk/quantity of unknowns on this project? |  | ⓘ
How confident are you the team will complete the project on time, and with high quality? |  | ⓘ
What documents you need: | What is also suggested, if applicable * :
FALSEFALSEFALSE
What documents are you choosing not to use, and why? This will help the team's determine what's needed and what's not so others can learn.
* The additional types of documentation may depend upon many factors within your project. For questions, reach out to the ITS PMO.
Note on K10: ITS PMO: A Duration example is: - July 1 Start date/kickoff - October 1 Go Live - November 1 End date/Close out project = Duration of 4 months
Note on K11: ITS PMO: Some projects do not have a budget. Budget is in regards to external labor, software, hardware costs needed to complete the project. It does not include LUC FTE labor hours. A budget will need to be approved for additional expenses for upcoming fiscal years, if applicable. Fiscal year starts July 1. Closely coordinate all budgeting provisions with your sponsor. For instance, a new software may require specific processing speeds and memory, Operating Systems, and certain network availability. The new software may require different coding and design skillsets that we may need to hire consultants to bridge the gap of knowledge. Training is usually an item that appears in budgets for new software implementations as well.
Note on K12: ITS PMO: Direct: Add together the # of people on the project team, the # of people who have access to the software, and those who consume information outputs from the software. Indirect: An example would be a report pulled from the software and shared as a daily practice with another department to complete their daily work is Indirect. However, the report data, look & feel, and speed to create the report may change with a new system. By understanding how many people are impacted, we can begin to understand the complexity of the project requirements.
Note on K15: ITS PMO: Some projects are small and do not have a VP involved; however, if there is a VP, you must identify how they want to receive updates about the project. An example of a project status with 2 VPs includes: - Bi-weekly status via email as well - Monthly, hi-level Executive Status to Executive and Project Sponsors In addition, if there are multiple VPs, there are different ways to organize and share information. If you have a project with multiple VPs, and would like to confirm your documentation approach, please reach out to the ITS PMO - pmo@luc.edu
Note on K16: ITS PMO: Plan of Record: The project is tied to a scheduled/planned University initiative and funds or internal resources have been planned for this project/work to be completed staring January or July. Identification of this type of project helps build awareness around risks, timeframes, level of project visibility to LUC Leadership, and potential cost/budget implications so they are managed properly. There may be a high-level of business benefit for these items, so ensuring the project & sponsors goals are proactively managed is expected.
Note on K17: ITS PMO: Leads are usually 1 person per department, key function on the project team, or contributing area who lead others within their area of direct reporting/influence when implementing a new project. They are able to provide guidance on specific aspects of how an area of the project's deliverables will be planned, implemented and supported after Go-Live. Leads are not everyone working on the project. Some people are Project Leads, meaning the ones providing Subject-Matter knowledge and Lead the project communication, tasks, schedule, and team collaboration for their area of influence on the project. Sometimes a specific Lead will be designated as the Project Manager for the project. The ficticious example below has 8 Leads, including the Project Manager: To shut down the existing Damen Food Court Hosted Website and set-up a new Damen Food Court Hosted Website, we would need a lead from the Student Services Dept (1) who currently manages the content on the website, Aramark (Food Services) (2), IT Networking (Bandwidth, etc) (3), University Marketing (digital design of the webpages) (4), and ITS Web Development team (business and technical requirements of how the future website will look and function) (5), the old hosting vendor (6), new hosting vendor (7), and Project Manager (8).
Note on K18: ITS PMO: Low Risk / Low Unknowns Example: A maintenance upgrade, that your group has implemented similar upgrades, several times, with the same employees, minimal updates/changes to the system, and seasoned department employee's who can validate the changes didn't cause errors in their daily work routine? Medium Risk / Medium Unknowns Example: Upgrading an existing system to a new platform with a different back-end technology and new IT Team members to do the conversion and testing. Also, the vendor has a new support escalation process for addressing software issues or concerns. High Degree of Risk / High Level of Unknowns Example: Turning off our old CRM Solution and implementing a new platform like SalesForce.com for our Athletics Department to solicit Alumni. The IT Skillset does not have experience with this platform (so they'll need to learn how it works) to understand what functionality Athletics wants to work, then they'll need training (to learn how to program it). Also the end-users (people using the old CRM solution) need training to familiarize themselves with the new CRM System (so they can transition using SalesForce.com). These are all HIGH degree's of complexity, difficulty, several unknowns, and lots of training for many departments within the organization.
Note on K19: ITS PMO: High Confidence Example: If the Executive or Project Sponsor supports and encourages the team to achieve the timeline, there have been no changes to the project team, and the project team is seasoned, and there are some technical unknowns but nothing critical on the project. Medium Confidence Example: If the Executive or Project Sponsor supports the project, but there are budget concerns or a few high-complexity tasks that have not been done before by the season project team, there could be some suprises on this project that were not anticipated due to complexity. Low Confidence Example: If the Executive or Project Sponsor provides limited support to the project team, changes their mind on the project scope, funding, timeline, or resources, or if there are a high-level of technical or business unknowns, risks or issues mentioned by the Sponsor (which is ok, sometimes projects have these factors and they can and will change) you may have a lower confidence based on project understanding and experience.

## Project Terms
Document Definitions
Each document is a tool to communicate specific project information. For more details, go to http://luc.edu/pmo
Document Name | Reason for using
PM Menu of Services | To request a Project Manager to assist with the project from the ITS PMO, and determine the PM's role on the project.
Project Request | To request a Project to be completed with ITS and approved & scheduled with the ITS Project Review Board.
Scope Statement | The goal, business benefit, expectations, timeframe and budget for the project.
Functional Specs | Specific details about "what" the business wants to change, update, enhanced and the "how" technical requirements to make that functionality work.
Risk Management | Tracks potential risks and their importance/impact if realized and ways to mitigate those risks, if needed.
Communication Plan | Organizes who will be given specific information, when it will be delivered (weekly, monthly, etc.) and in what format or channel to use (email, status, meeting, etc).
Hi-Level Project Plan | Lists the hi-level milestones (with minimal detailed tasks) with expected dates and owner for each milestone.
Detailed Project Plan | Lists the milestones and detailed steps with expected dates and resources to complete each task.
Budget Plan | Includes any costs to your project, consulting, training, hardware or software costs, etc. that will be needed to complete your project.
Work Breakdown Structure | The WBS shows the relationships among all the project deliverables & high-level areas of responsibility. It can be organized by Work Packages, Phases, or Major Deliverables.
Action Items List | Tracks all items that team members will be completing throughout the project to ensure sub-tasks and goals are kept on track.
Agenda & Minutes | Meetings with agendas help the team prepare and focus on the meeting goals. Minutes provide a recap of who attended & what items were discussed.
Bi-Weekly Status | Usually completed with a Word template, provides a detailed update on the project health, key initiatives, team activities, risks, issues, and next steps.
Executive Status | Usually completed with a Word template, provides a hi-level update on the project health, key initiatives, team activities, risks, issues, and next steps.
Project Close Out | Provides an update & transfer of remaining tasks from project to business ownership and gather Sponsors feedback on how the project was managed by the Lead/PM.
Project Vocabulary
This is a subset of project terms frequently used on Loyola's ITS projects. For more details, go to http://www.luc.edu/pmo
Term | Definition
Duration | From the moment the PM/Lead is assigned to the Project until Project Close Out, this length of time (calendar days) is the project duration.
Business Benefit | The Business Benefit answers these questions: What's the reason for implementing this project? What problems will it solve? What enhancements/ benefits will it provide?
Risks | Is an uncertain event or condition that if it occurs, has a positive or negative effect on the project's goals.
Knowns | Knowns are things that are in our project plan.
Unknowns | Unknowns are: things we've identified and need to explore more; things that forgotten/were not planned; or unforseen events (i.e. natural disaster) or complex & uncertain tasks.
Lead | Lead's are primarily responsible for aspects or modules of a project usually Technical leads (for technical components) and Functional Leads (for business-facing components).
Project Start | The date the project manager formally hold a kick-off meeting, or initial project pre-work begins on a project and a Lead or PM holds their first meeting with the team.
Go-Live | The date the project will be put into Production (meaning, when people in the various departments will stop using the old system and start using the updated or new system).
Project Completion | After Go-Live of the project, IT post-Go Live Support, business hand-off is complete, and the Close Out document is complete, the project is formally closed.
ITS PMO | Group within ITS that suggests & maintains project standards in collaboration with all of LUC ITS.
Project Health | Based on all the critical factors of the project (Scope, Schedule, Budget, Risks, Quality), select a health color to communicate the average health of the project.
Helpful Links
ITS VPMO | https://www.luc.edu/its/vpmo/
IT Project Request | https://www.luc.edu/media/lucedu/pmo/pdfs/system_service_request.doc
Note on B13: ITS PMO: Drafted by you and your manager, and/or sponsor(s)

## NEW SCORING PAGE (hidden)
What is the duration of this project based on the Project Start date through the Project End date? (Q1) |  | What documents you need: | What is also suggested, if applicable:
Less than 1 mo | 0 | Hi-Level Project Plan
1-3 mo | 1 | Hi-Level Project Plan | Detailed Project plan
3-6 mo | 2 | Hi-Level Project Plan | Detailed Project plan
6-18 mo | 3 | Detailed Project plan, Risk Management Plan
Over 18 mo | 4 | Detailed Project plan, Risk Management Plan
Will this project drive any new capital or operating expenditures? (Q2)
No | 0
Yes | 1 | Budget Plan
How many people will be impacted (directly and indirectly) by this project's final deliverable? (Q3)
Less than 10 | 0 |  | Communication Plan
10-25 | 1 |  | Communication Plan
25-50 | 2 | Communication Plan
Over 50 | 3 | Communication Plan
How many VPs are involved with your project? (Q4)
None | 0 | Bi-weekly Status
1 | 1 | Bi-weekly Status | Executive Status
2 | 2 | Bi-weekly Status, Executive Status
Over 2 | 3 | Bi-weekly Status, Executive Status
Has this project been approved through the Plan of Record? (Q5)
No | 0 | PM Menu of Services, Project Request
Yes | 1 | PM Menu of Services
How many leads are on this project? (Q6)
1-2 | 1 | Agenda & Minutes | Action Items List, Work Breakdown Structure
3-5 | 2 | Agenda & Minutes, Action Items List | Work Breakdown Structure
Over 5 | 3 | Agenda & Minutes, Action Items List | Work Breakdown Structure
What is the perceived level of difficultly/quantity of unknowns on this project? (Q7)
Minimal Risk & Limited Unknowns | 0 | Scope Statement | Functional Specs
Some Risk & Some Unknowns | 1 | Scope Statement, Functional Specs, Risk Management Plan
High Risk & Several Unknowns | 2 | Scope Statement, Functional Specs, Risk Management Plan
How confident are you the team will complete the project on time, and with high quality? (Q8)
High Confidence | 0 | Project Close Out
Medium Confidence | 1 | Project Close Out
Low Confidence | 2 | Project Close Out

## Sheet2 (hidden)
Less than 1 mo | 0
1-3 mo | 1
3-6 mo | 2
6-18 mo | 3
Over 18 mo | 4
No | 0
Yes | 1
Less than 10 | 0
10-25 | 1
25-50 | 2
Over 50 | 3
None | 0
One | 1
Two | 2
Over 2 | 3
No | 0
Yes | 1
1-2 | 1
3-5 | 2
Over 5 | 3
0 to 1 | 0
2-3 | 1
4-5 | 2
Over 5 | 3
Minimal Risk & Limited Unknowns | 0
Some Risk & Some Unknowns | 1
High Risk & Several Unknowns | 2
High Confidence | 0
Medium Confidence | 1
Low Confidence | 2
No | 0
Yes | 1
No | 0
Yes | 1
No | 0
Yes | 1
No | 0
Yes | 1

## Ranking Criteria (hidden)
Primary Questions |  |  |  | Option 1 | Option 2 | Option 3 | Option 4 | Option 5
What is the duration of this project? |  |  | Info | 0 | 1 | 2 | 3 | 4
What is the budget range for this project? |  |  | Info | 0 | 1 | 2 | 3
How many people (direct & indirect) will be impacted by this project's final deliverable? |  |  | Info | 0 | 1 | 2 | 3
Secondary Questions
How many VP's are on your project? |  |  | Info | 0 | 1 | 2 | 3
Is this tied to an Enterprise or Plan of Record Initiative? |  |  | Info | 0 | 1
How many leads are on this project? |  |  | Info | 0 | 1 | 2 | 3
How many unique departments will be consulted about this project's goals? |  |  | Info | 0 | 1 | 2 | 3
What is the perceived level of difficultly/quantity of unknowns on this project? |  |  | Info | 0 | 1 | 2 | 3
How confident are you the team will complete the project on time, and with high quality? |  |  | Info | 0 | 1 | 2 | 3
Supplemental Questions
Check all that apply as to why this project is being undertaken? (all would be 1 point)
- President's Initiative |  |  | Info | 0 | 1
- Regulatory or Compliance Project |  |  | Info | 0 | 1
- Governance Project |  |  | Info | 0 | 1
- Budget Saving project |  |  | Info | 0 | 1
Primary & Secondary Ranges | What documents you need: | What is also suggested, if applicable: |  |  |  |  | What's helpful when you have VP's or large #'s of leads: |  | Cutoff
0-5 | Business Requirements, Action Items, Bi-Weekly Status, Project Close out | Scope, Meeting Agenda & Minutes |  |  |  |  | Executive Status, Decision Change Log |  | 5
6-11 | Scope, Project Plan, Business Requirements, Action Items, Bi-Weekly Status, Project Close out, Meeting Agenda & Minutes | Budget plan, Technical Requirements, Budget plan |  |  |  |  | Communication Plan, Executive Status, Change Decision Log |  | 11
12-18 | Scope, Business Requirements, Detailed Project Plan, Action Items, Meeting Agenda & Minutes, Bi-Weekly Status, Project Close out, Lessons Learned | PMO Menu of Services, SI&C Project Request, Technical Requirements, Budget plan |  |  |  |  | Communication Plan, Risk Registry, Executive Status, Change Decision Log |  | 18
19 and above | PMO Menu of Services, SI&C Project Request, Scope, Business Requirements, Detailed Project Plan, Action Items, Meeting Agenda & Minutes, Bi-Weekly Status, Project Close out, Lessons Learned | Technical Requirements, Budget plan |  |  |  |  | Communication Plan, Risk Registry, Executive Status, Change Decision Log |  | 19
* The additional type of documentation may depend upon, the numbers of VP's on your project
Note on J3: Tomley, Heather: Less than 1 mo = 0 1-3 mo = 1 3-6 mo = 2 6-18 mo = 3 Over 18 mo = 4
Note on J4: Tomley, Heather: Less than $100K = 0 $150-250K = 1 $250-500K = 2 Over $500K = 3
Note on J5: Tomley, Heather: Less than 10 = 0 10-25 = 1 25-50 = 2 over 50 = 3
Note on J8: Tomley, Heather: None = 0 1 = 1 2 = 2 Over 2 = 3
Note on J9: Tomley, Heather: No = 0 Yes = 1
Note on J10: Tomley, Heather: None = 0 1-2 = 1 3-5 = 2 Over 5 = 3
Note on J11: Tomley, Heather: 0 to 1 = 0 2-3 = 1 4-5 = 2 Over 5 = 3
Note on J12: Tomley, Heather: Minimal unknowns & limited difficulty = 0 Some unknowns & some difficulty = 1 Many unknowns, high level of difficulty = 2 Never done before = 3
Note on J13: Tomley, Heather: High Confidence = 0 Medium Confidence = 1 Low Confidence = 2 Expect the schedule to change during the first 1/2 of the project duration = 3
Note on J17: Tomley, Heather: No = 0 Yes = 1
Note on J18: Tomley, Heather: No = 0 Yes = 1
Note on J19: Tomley, Heather: No = 0 Yes = 1
Note on J20: Tomley, Heather: No = 0 Yes = 1